## Sheet1
Functionality | Description | Impact | Dependencies | Ranking | Timelines | Type | Status | Notes | Supplemental notes | Discover Review
Number (N) Invited | Track number (N) of patients who received invitations | Core metric for outreach effectiveness | Should be part of analytics dashboard in a section where we are able to track enrollment metrics (e.g., consented, declined, how many invites were sent out, etc.) | High | 2025 Q4 | Recruitment Analytics | Planned | Updated Clarifying Question for meeting: When you say 'number of invited patients,' which point in the funnel are you trying to measure? Option A: Gross invitations sent (total emails dispatched) Option B: Patients who started the assessment (actual engagement) Option C: Patients who completed the assessment and are eligible for Discover Options B or C would give you a more actionable number since they reflect real patient engagement, not just email volume. | 1. Option B – Not Viable Requirement to enter Discover is based on the patient being enrolled in the program. If they don't complete the assessment, they're not enrolled—so Option B doesn't work. 2. Option C – Preferred Appears to be the preferred approach, but needs final confirmation. 3. New Requirement (Potential) If a patient does not opt out of the invitation/reminder for their primary/entry program but doesn't start or complete the assessment, send them a Discover reminder as well. 3.a. Follow-up Question: Would the Discover reminder be: A standalone message directing them to the Discover website? OR A message encouraging them to enter through the assessment/appropriate channel? 4. Analytics Request They would like the ability to analyze by program channel. | Reviewed Option C, okay to proceed once final confirmation is received on viability. For 3a, can you clarify if through assessment/appropriate channel means that the patient would be linked to where they left off after completing their clinical program assessment (I.e., they get to the accordion to see the intro about Discover and navigate away/close the window and then receive a reminder.)
% Consented vs. Declined Consent | Compare consent vs. decline consent rates | Critical for recruitment strategy | Status logging from counts we already track under Manage Participants > Recent Activity > Activity Result | High | 2025 Q4 | Recruitment Analytics | Completed
Program Recruitment Comparison | Identify recruitment volume by program | Reveals geographic or operational biases | This is tracked under Channel Enrollment but will be essential for us to split this out as we integrate with more genomics programs (i.e., GenoRX, etc.) | Medium | 2026 Q1 | Recruitment Analytics | Planned
Consent Flow Drop-off Tracking | See where users stop in the consent process | Improves UX and conversion | Needs event tracking and funnel analytics | Medium | 2026 Q1 | Recruitment Analytics | Planned
Email Engagement Tracking | Monitor if emails are opened or ignored | Optimizes communication strategy | Requires integration with email platform and privacy compliance | High | 2025 Q4 | Recruitment Analytics | Planned | I'd caution against using email opens as a meaningful metric. Palbox tracks opens by detecting when the email client requests images. If a patient's email client or browser blocks images by default — which is increasingly common — they can read the entire email but it won't register as opened. This means open rates will consistently under-report actual engagement. That's why I recommend measuring from assessment started or assessment completed — those are definitive actions we can track with confidence. | Email Open Tracking: Stakeholder concurs — Paubox method is unreliable. Removed from scope. New Request — Rejected Email Tracking: • Short-term: Manual pull on a monthly basis, present in recurring monthly meeting • Long-term: Potentially integrate into the analytics dashboard • Dependency: Check with Brett if dashboard integration is supportable | Agree to move forward with rejected email tracking with long-term intergration into the analytics dashboard. Advise that we integrate it as an actionable metric that project coordinators can click on to use an alternative pathway to contact the patient (e.g., email kicked back, project coordinator reviews kickbacks via analytics dashboard and can click to send SMS messages to those patients.
Reminder Email Opt-Out Tracking | Monitor which users opt out of reminder emails | Ensures effective tracking should a participant want to change their mind in the future+C9I7C7 | Requires tracking individual and aggregated filter options | High | 2025 Q4 | Recruitment Analytics | Planned | For reminder email opt-out tracking, which scope are you looking for? Option A: Discover-specific reminder opt-outs only (patients who reached Discover and opted out of its reminders) Option B: All reminder opt-outs across upstream programs (Prevention4ME, Precision4ME, GenoRX) that feed into Discover Option C: Both — a combined view showing opt-outs at each program stage Keep in mind: With Option B or C, a patient may opt out of upstream reminders before they ever know Discover is part of the journey. Do you want visibility into that, or only patients who explicitly opted out of Discover communications? | Updated Requirement: Reminder Email Opt-Out Tracking • Scope: Discover-specific reminders only (not upstream programs) • Format: Aggregated visualization (chart), not patient-level data • Metric: Reminders Received vs. Opted Out | Reviewed and okay to proceed with no additional notes.
Registry Decline Tracking | Track users who decline to participate in the registry entirely | All right, for the reminder email tracking, they're just looking to get the discover specific reminder opt out. But what they want is aggregated numbers. Not so they want it basically some type of chart that shows aggregated who's received versus who's opted out. | Workflow integrated already for forms | High | 2025 Q4 | Recruitment Analytics | Completed
On-demand Patient Lists | Need to be able to pull list of patients who have declined to participate in the registry, consented, opted-in for future research, etc. | Applicable for future studies that we want to identify cohorts for | Would need to include different filtering for identifying cohorts based on current metadata | High | 2025 Q4 | Recruitment Analytics | Planned | Currently you can filter by patient status and download lists. Can you help me understand where the gap is? Access Issue: Do you need someone without full system access to pull these reports? Usability Issue: Is the current filter/download process too cumbersome or slow? Format Issue: Do you need the data in a different format or with additional fields? Automation Issue: Are you looking for scheduled/automated reports instead of manual pulls? Understanding what's friction today will help us scope the right solution. | Updated Requirement: On-Demand Patient Lists • Status: Deferred to review session • Action: Add to agenda for 1:1 with Nick (next Monday) • Goal: Understand the gap between current filter/download capability and what they're envisioning | Reviewed requirements and no further notes. Okay to move forward.
Time on Consent Form | Track amount of time spent on each consent form page | Indicates how patients are interacting with the content of the consent form | How do we facilitate a patient's time completing the consent and how we add it to different programs/flow/experience | Medium | 2026 Q1 | Recruitment Analytics | Planned
Recruitment Comparison by Demographics | Demographic comparison for various filters (gender, race/ethnicity, age, etc.) | Important for understanding various demographic filtering to improve patient engagement | Existing metadata that needs to be sorted | Medium | 2026 Q1 | Recruitment Analytics | Completed
Saliva Kit Ordering | Enables Discover Research team to order saliva kits via Propel dashboard for participants that opted-in for population sequencing protocol | Reduces manual workflows and increases effiency for large-scale population sequencing across broad and program-specific recruitment pathways | Requires integration with Genotek | Medium | 2026 Q1 | Operational Logistics | Planned
MyChart Recruitment Cross Validation | Cross validate participants entering through the MyChart recruitment pathway against existing e-consent records in Propel to prevent duplicate enrollment from other recruitment pathways. Once cross validation is confirmed, a patient is allowed to proceed with consent if no consent exists or presented with a screen that notes that they have already been enrolled if validation notes a consent exists | Prevents redundant consent submission, and reduces confusion for participants recruited from other recruitment pathways | Requires cross-validation logic to identify matches based on MRN, name or unique hashed identifiers | High | 2025 Q4 | Data Integrity/Recruitment Workflow | Planned | Enage with Brett on.
Multi-Study Dashboard | Show a personalized list of available studies on the patient dashboard; each study appears as a collapsible accordion with shorthand details and a "Learn more/Sign Up" action | Centralizes options, reduces navigation friction, and increases conversion by surfacing all eligible studies in one place with quick-scan information | Requires incorporation of IRB-approved study materials, appropriate navigation for entering/returning/exiting materials to ensure clear division of which study belongs to which collapsible accordion, notation of participant status (e.g., enrolled, withdrawn, not yet enrolled) | Medium | 2026 Q1 | Participant Experience/Recruitment UX | Planned
SMS Outreach Reminders | Allows for researchers to reach out to patients via SMS through the platform | Increases multichannel outreach to potential participants | Should go out at the same time as email reminders | High | 2026 Q1 | Participant Experience/Recruitment UX | Planned | For SMS outreach reminders, here's what we need from you: Coordinate with Andrew — he'll work with you to gather the required campaign information for Amazon approval Timeline Expectation: Typically ~2 weeks for approval, but could extend if iterations are needed Reference: Precision4ME had some friction but still resolved within 2 weeks What we need to kick this off: The sooner you connect with Andrew, the sooner we can submit. What's your availability to start that conversation? | Updated Requirement: SMS Outreach Reminders • Stakeholder needs to provide: 2 invitation samples + 2 reminder samples • Andrew will send: Current SMS templates as a baseline to start from • Then: Submit to Amazon for campaign approval (~2 weeks) | Nick to reach out to Andrew for template. Draft language in process with Discover Team.
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: May need to change this based on larger items for 2026 Q1. Reply: Lab ordering, etc. (Top 3)