## Summary
UAT Test Package Summary
Generated: 2025-12-18 16:50
Source: Propel Functionalities Request.xlsx
Overview
Total User Stories: | 11
Total Test Cases: | 207
Stories by Priority
Critical | 0
High | 6
Medium | 5
Low | 0
Test Cases by Type
Happy Path | 76
Negative | 54
Edge Case | 22
Boundary | 0
Test Cases by MoSCoW
Must Have | 126
Should Have | 59
Could Have | 22
Won't Have | 0
Items Requiring Attention
Number (N) Invited | vague_language, needs_clarification
Program Recruitment Comparison | vague_language
Reminder Email Opt-Out Tracking | needs_clarification
On-demand Patient Lists | vague_language, needs_clarification
SMS Outreach Reminders | needs_clarification

## Test Case Master
Test ID | Source Story | Category | Title | Test Type | Pre-Requisites | Test Steps | Expected Results | MoSCoW | Est. Time | Notes
TEST2-RECRUIT-001 | TEST2-RECRUIT-001 | RECRUIT | Verify Number (N) Invited | Happy Path | • User is logged in with appropriate permissions • Test data is available in the system • Recruitment analytics module is enabled | 1. Navigate to the relevant module/page 2. Verify the feature is accessible 3. Observe the dashboard/display loads 4. Verify data is displayed correctly 5. Test any filters or date range selectors 6. Verify data accuracy against source | **Expected Behavior (Gherkin):** Given the user has appropriate permissions When they access the track number (N) of patients who receive feature Then the feature works as expected **Specific Outcomes:** ✓ Count of invited patients displays accurately ✓ Metrics are segmented by program/channel ✓ Funnel shows progression from invitation to enrollment ✓ Aggregated view available (not patient-level by default) ✓ Data exportable for offline analysis | Must Have | 5-10 min | Validates acceptance criteria for TEST2-RECRUIT-001
TEST2-RECRUIT-002 | TEST2-RECRUIT-001 | RECRUIT | Validate: Count of invited patients displays accurately | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Count of invited patients displays accurately 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Count of invited patients displays accurately | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-001
TEST2-RECRUIT-003 | TEST2-RECRUIT-001 | RECRUIT | Validate: Metrics are segmented by program/channel | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Metrics are segmented by program/channel 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Metrics are segmented by program/channel | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-001
TEST2-RECRUIT-004 | TEST2-RECRUIT-001 | RECRUIT | Validate: Funnel shows progression from invitation to enrollment | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Funnel shows progression from invitation to enrollment 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Funnel shows progression from invitation to enrollment | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-001
TEST2-RECRUIT-005 | TEST2-RECRUIT-001 | RECRUIT | Validate: Aggregated view available (not patient-level by default) | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Aggregated view available (not patient-level by default) 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Aggregated view available (not patient-level by default) | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-001
TEST2-RECRUIT-006 | TEST2-RECRUIT-001 | RECRUIT | Validate: Data exportable for offline analysis | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Data exportable for offline analysis 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Data exportable for offline analysis | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-001
TEST2-RECRUIT-007 | TEST2-RECRUIT-001 | RECRUIT | Verify behavior with insufficient permissions | Negative | • User is logged in | 1. Log in as user without required permissions 2. Attempt to access the feature 3. Observe system response | **Given** a user without permissions **When** they attempt to access the feature **Then** access is denied with appropriate message | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-001
TEST2-RECRUIT-008 | TEST2-RECRUIT-001 | RECRUIT | Verify dashboard with no data | Negative | • User is logged in | 1. Access dashboard with empty dataset 2. Observe display behavior | **Then** empty state message is displayed **And** no errors occur | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-001
TEST2-RECRUIT-009 | TEST2-RECRUIT-001 | RECRUIT | Verify behavior with invalid/malformed input | Negative | • User is logged in | 1. Enter invalid data in required fields 2. Attempt to submit/save 3. Observe validation messages | **Given** invalid input is provided **When** the user submits **Then** clear validation errors are displayed **And** data is not saved | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-001
TEST2-RECRUIT-010 | TEST2-RECRUIT-001 | RECRUIT | Verify with large dataset (10,000+ records) | Edge Case | • User is logged in | 1. Load dashboard with 10,000+ records 2. Observe load time and performance 3. Test pagination/scrolling | **Then** data loads within acceptable time (<10s) **And** pagination works correctly **And** no performance degradation | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-001
TEST2-RECRUIT-011 | TEST2-RECRUIT-001 | RECRUIT | Verify with extreme date range | Edge Case | • User is logged in | 1. Select date range spanning multiple years 2. Observe data aggregation | **Then** data aggregates correctly **And** display remains readable | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-001
TEST2-RECRUIT-012 | TEST2-RECRUIT-002 | RECRUIT | Verify Program Recruitment Comparison | Happy Path | • User is logged in with appropriate permissions • Test data is available in the system • Recruitment analytics module is enabled | 1. Navigate to the relevant module/page 2. Verify the feature is accessible 3. Observe the dashboard/display loads 4. Verify data is displayed correctly 5. Test any filters or date range selectors 6. Verify data accuracy against source | **Expected Behavior (Gherkin):** Given the user has appropriate permissions When they access the identify recruitment volume by program feature Then the feature works as expected **Specific Outcomes:** ✓ Count of patients patients displays accurately ✓ Metrics are segmented by program/channel ✓ Funnel shows progression from invitation to enrollment ✓ Aggregated view available (not patient-level by default) ✓ Data exportable for offline analysis | Should Have | 5-10 min | Validates acceptance criteria for TEST2-RECRUIT-002
TEST2-RECRUIT-013 | TEST2-RECRUIT-002 | RECRUIT | Validate: Count of patients patients displays accurately | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Count of patients patients displays accurately 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Count of patients patients displays accurately | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-002
TEST2-RECRUIT-014 | TEST2-RECRUIT-002 | RECRUIT | Validate: Metrics are segmented by program/channel | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Metrics are segmented by program/channel 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Metrics are segmented by program/channel | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-002
TEST2-RECRUIT-015 | TEST2-RECRUIT-002 | RECRUIT | Validate: Funnel shows progression from invitation to enrollment | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Funnel shows progression from invitation to enrollment 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Funnel shows progression from invitation to enrollment | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-002
TEST2-RECRUIT-016 | TEST2-RECRUIT-002 | RECRUIT | Validate: Aggregated view available (not patient-level by default) | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Aggregated view available (not patient-level by default) 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Aggregated view available (not patient-level by default) | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-002
TEST2-RECRUIT-017 | TEST2-RECRUIT-002 | RECRUIT | Validate: Data exportable for offline analysis | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Data exportable for offline analysis 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Data exportable for offline analysis | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-002
TEST2-RECRUIT-018 | TEST2-RECRUIT-002 | RECRUIT | Verify behavior with insufficient permissions | Negative | • User is logged in | 1. Log in as user without required permissions 2. Attempt to access the feature 3. Observe system response | **Given** a user without permissions **When** they attempt to access the feature **Then** access is denied with appropriate message | Should Have | 3-5 min | Negative test for TEST2-RECRUIT-002
TEST2-RECRUIT-019 | TEST2-RECRUIT-002 | RECRUIT | Verify dashboard with no data | Negative | • User is logged in | 1. Access dashboard with empty dataset 2. Observe display behavior | **Then** empty state message is displayed **And** no errors occur | Should Have | 3-5 min | Negative test for TEST2-RECRUIT-002
TEST2-RECRUIT-020 | TEST2-RECRUIT-002 | RECRUIT | Verify behavior with invalid/malformed input | Negative | • User is logged in | 1. Enter invalid data in required fields 2. Attempt to submit/save 3. Observe validation messages | **Given** invalid input is provided **When** the user submits **Then** clear validation errors are displayed **And** data is not saved | Should Have | 3-5 min | Negative test for TEST2-RECRUIT-002
TEST2-RECRUIT-021 | TEST2-RECRUIT-002 | RECRUIT | Verify with large dataset (10,000+ records) | Edge Case | • User is logged in | 1. Load dashboard with 10,000+ records 2. Observe load time and performance 3. Test pagination/scrolling | **Then** data loads within acceptable time (<10s) **And** pagination works correctly **And** no performance degradation | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-002
TEST2-RECRUIT-022 | TEST2-RECRUIT-002 | RECRUIT | Verify with extreme date range | Edge Case | • User is logged in | 1. Select date range spanning multiple years 2. Observe data aggregation | **Then** data aggregates correctly **And** display remains readable | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-002
TEST2-RECRUIT-023 | TEST2-RECRUIT-003 | RECRUIT | Verify Consent Flow Drop-off Tracking | Happy Path | • User is logged in with appropriate permissions • Test data is available in the system • Recruitment analytics module is enabled | 1. Navigate to the relevant module/page 2. Verify the feature is accessible 3. Observe the dashboard/display loads 4. Verify data is displayed correctly 5. Test any filters or date range selectors 6. Verify data accuracy against source | **Expected Behavior (Gherkin):** Given the user has appropriate permissions When they access the see where users stop in the consent proc feature Then the feature works as expected **Specific Outcomes:** ✓ Count of patients patients displays accurately ✓ Metrics are segmented by program/channel ✓ Funnel shows progression from invitation to enrollment ✓ Aggregated view available (not patient-level by default) ✓ Data exportable for offline analysis | Should Have | 5-10 min | Validates acceptance criteria for TEST2-RECRUIT-003
TEST2-RECRUIT-024 | TEST2-RECRUIT-003 | RECRUIT | Validate: Count of patients patients displays accurately | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Count of patients patients displays accurately 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Count of patients patients displays accurately | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-003
TEST2-RECRUIT-025 | TEST2-RECRUIT-003 | RECRUIT | Validate: Metrics are segmented by program/channel | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Metrics are segmented by program/channel 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Metrics are segmented by program/channel | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-003
TEST2-RECRUIT-026 | TEST2-RECRUIT-003 | RECRUIT | Validate: Funnel shows progression from invitation to enrollment | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Funnel shows progression from invitation to enrollment 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Funnel shows progression from invitation to enrollment | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-003
TEST2-RECRUIT-027 | TEST2-RECRUIT-003 | RECRUIT | Validate: Aggregated view available (not patient-level by default) | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Aggregated view available (not patient-level by default) 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Aggregated view available (not patient-level by default) | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-003
TEST2-RECRUIT-028 | TEST2-RECRUIT-003 | RECRUIT | Validate: Data exportable for offline analysis | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Data exportable for offline analysis 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Data exportable for offline analysis | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-003
TEST2-RECRUIT-029 | TEST2-RECRUIT-003 | RECRUIT | Verify behavior with insufficient permissions | Negative | • User is logged in | 1. Log in as user without required permissions 2. Attempt to access the feature 3. Observe system response | **Given** a user without permissions **When** they attempt to access the feature **Then** access is denied with appropriate message | Should Have | 3-5 min | Negative test for TEST2-RECRUIT-003
TEST2-RECRUIT-030 | TEST2-RECRUIT-003 | RECRUIT | Verify dashboard with no data | Negative | • User is logged in | 1. Access dashboard with empty dataset 2. Observe display behavior | **Then** empty state message is displayed **And** no errors occur | Should Have | 3-5 min | Negative test for TEST2-RECRUIT-003
TEST2-RECRUIT-031 | TEST2-RECRUIT-003 | RECRUIT | Verify behavior with invalid/malformed input | Negative | • User is logged in | 1. Enter invalid data in required fields 2. Attempt to submit/save 3. Observe validation messages | **Given** invalid input is provided **When** the user submits **Then** clear validation errors are displayed **And** data is not saved | Should Have | 3-5 min | Negative test for TEST2-RECRUIT-003
TEST2-RECRUIT-032 | TEST2-RECRUIT-003 | RECRUIT | Verify with large dataset (10,000+ records) | Edge Case | • User is logged in | 1. Load dashboard with 10,000+ records 2. Observe load time and performance 3. Test pagination/scrolling | **Then** data loads within acceptable time (<10s) **And** pagination works correctly **And** no performance degradation | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-003
TEST2-RECRUIT-033 | TEST2-RECRUIT-003 | RECRUIT | Verify with extreme date range | Edge Case | • User is logged in | 1. Select date range spanning multiple years 2. Observe data aggregation | **Then** data aggregates correctly **And** display remains readable | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-003
TEST2-RECRUIT-034 | TEST2-RECRUIT-004 | RECRUIT | Verify Email Engagement Tracking | Happy Path | • User is logged in with appropriate permissions • Test data is available in the system • Recruitment analytics module is enabled | 1. Navigate to the relevant module/page 2. Verify the feature is accessible 3. Observe the dashboard/display loads 4. Verify data is displayed correctly 5. Test any filters or date range selectors 6. Verify data accuracy against source | **Expected Behavior (Gherkin):** Given the user has appropriate permissions When they access the monitor if emails are opened or ignored feature Then the feature works as expected **Specific Outcomes:** ✓ Count of patients patients displays accurately ✓ Metrics are segmented by program/channel ✓ Funnel shows progression from invitation to enrollment ✓ Aggregated view available (not patient-level by default) ✓ Data exportable for offline analysis | Must Have | 5-10 min | Validates acceptance criteria for TEST2-RECRUIT-004
TEST2-RECRUIT-035 | TEST2-RECRUIT-004 | RECRUIT | Validate: Count of patients patients displays accurately | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Count of patients patients displays accurately 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Count of patients patients displays accurately | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-004
TEST2-RECRUIT-036 | TEST2-RECRUIT-004 | RECRUIT | Validate: Metrics are segmented by program/channel | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Metrics are segmented by program/channel 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Metrics are segmented by program/channel | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-004
TEST2-RECRUIT-037 | TEST2-RECRUIT-004 | RECRUIT | Validate: Funnel shows progression from invitation to enrollment | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Funnel shows progression from invitation to enrollment 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Funnel shows progression from invitation to enrollment | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-004
TEST2-RECRUIT-038 | TEST2-RECRUIT-004 | RECRUIT | Validate: Aggregated view available (not patient-level by default) | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Aggregated view available (not patient-level by default) 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Aggregated view available (not patient-level by default) | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-004
TEST2-RECRUIT-039 | TEST2-RECRUIT-004 | RECRUIT | Validate: Data exportable for offline analysis | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Data exportable for offline analysis 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Data exportable for offline analysis | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-004
TEST2-RECRUIT-040 | TEST2-RECRUIT-004 | RECRUIT | Verify behavior with insufficient permissions | Negative | • User is logged in | 1. Log in as user without required permissions 2. Attempt to access the feature 3. Observe system response | **Given** a user without permissions **When** they attempt to access the feature **Then** access is denied with appropriate message | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-004
TEST2-RECRUIT-041 | TEST2-RECRUIT-004 | RECRUIT | Verify dashboard with no data | Negative | • User is logged in | 1. Access dashboard with empty dataset 2. Observe display behavior | **Then** empty state message is displayed **And** no errors occur | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-004
TEST2-RECRUIT-042 | TEST2-RECRUIT-004 | RECRUIT | Verify behavior with invalid/malformed input | Negative | • User is logged in | 1. Enter invalid data in required fields 2. Attempt to submit/save 3. Observe validation messages | **Given** invalid input is provided **When** the user submits **Then** clear validation errors are displayed **And** data is not saved | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-004
TEST2-RECRUIT-043 | TEST2-RECRUIT-004 | RECRUIT | Verify with large dataset (10,000+ records) | Edge Case | • User is logged in | 1. Load dashboard with 10,000+ records 2. Observe load time and performance 3. Test pagination/scrolling | **Then** data loads within acceptable time (<10s) **And** pagination works correctly **And** no performance degradation | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-004
TEST2-RECRUIT-044 | TEST2-RECRUIT-004 | RECRUIT | Verify with extreme date range | Edge Case | • User is logged in | 1. Select date range spanning multiple years 2. Observe data aggregation | **Then** data aggregates correctly **And** display remains readable | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-004
TEST2-RECRUIT-045 | TEST2-RECRUIT-005 | RECRUIT | Verify Reminder Email Opt-Out Tracking | Happy Path | • User is logged in with appropriate permissions • Test data is available in the system • Recruitment analytics module is enabled | 1. Navigate to the relevant module/page 2. Verify the feature is accessible 3. Observe the dashboard/display loads 4. Verify data is displayed correctly 5. Test any filters or date range selectors 6. Verify data accuracy against source | **Expected Behavior (Gherkin):** Given the user has appropriate permissions When they access the monitor which users opt out of reminder feature Then the feature works as expected **Specific Outcomes:** ✓ Count of patients patients displays accurately ✓ Metrics are segmented by program/channel ✓ Funnel shows progression from invitation to enrollment ✓ Aggregated view available (not patient-level by default) ✓ Data exportable for offline analysis | Must Have | 5-10 min | Validates acceptance criteria for TEST2-RECRUIT-005
TEST2-RECRUIT-046 | TEST2-RECRUIT-005 | RECRUIT | Validate: Count of patients patients displays accurately | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Count of patients patients displays accurately 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Count of patients patients displays accurately | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-005
TEST2-RECRUIT-047 | TEST2-RECRUIT-005 | RECRUIT | Validate: Metrics are segmented by program/channel | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Metrics are segmented by program/channel 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Metrics are segmented by program/channel | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-005
TEST2-RECRUIT-048 | TEST2-RECRUIT-005 | RECRUIT | Validate: Funnel shows progression from invitation to enrollment | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Funnel shows progression from invitation to enrollment 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Funnel shows progression from invitation to enrollment | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-005
TEST2-RECRUIT-049 | TEST2-RECRUIT-005 | RECRUIT | Validate: Aggregated view available (not patient-level by default) | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Aggregated view available (not patient-level by default) 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Aggregated view available (not patient-level by default) | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-005
TEST2-RECRUIT-050 | TEST2-RECRUIT-005 | RECRUIT | Validate: Data exportable for offline analysis | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Data exportable for offline analysis 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Data exportable for offline analysis | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-005
TEST2-RECRUIT-051 | TEST2-RECRUIT-005 | RECRUIT | Verify behavior with insufficient permissions | Negative | • User is logged in | 1. Log in as user without required permissions 2. Attempt to access the feature 3. Observe system response | **Given** a user without permissions **When** they attempt to access the feature **Then** access is denied with appropriate message | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-005
TEST2-RECRUIT-052 | TEST2-RECRUIT-005 | RECRUIT | Verify dashboard with no data | Negative | • User is logged in | 1. Access dashboard with empty dataset 2. Observe display behavior | **Then** empty state message is displayed **And** no errors occur | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-005
TEST2-RECRUIT-053 | TEST2-RECRUIT-005 | RECRUIT | Verify behavior with invalid/malformed input | Negative | • User is logged in | 1. Enter invalid data in required fields 2. Attempt to submit/save 3. Observe validation messages | **Given** invalid input is provided **When** the user submits **Then** clear validation errors are displayed **And** data is not saved | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-005
TEST2-RECRUIT-054 | TEST2-RECRUIT-005 | RECRUIT | Verify with large dataset (10,000+ records) | Edge Case | • User is logged in | 1. Load dashboard with 10,000+ records 2. Observe load time and performance 3. Test pagination/scrolling | **Then** data loads within acceptable time (<10s) **And** pagination works correctly **And** no performance degradation | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-005
TEST2-RECRUIT-055 | TEST2-RECRUIT-005 | RECRUIT | Verify with extreme date range | Edge Case | • User is logged in | 1. Select date range spanning multiple years 2. Observe data aggregation | **Then** data aggregates correctly **And** display remains readable | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-005
TEST2-RECRUIT-056 | TEST2-RECRUIT-006 | RECRUIT | Verify On-demand Patient Lists | Happy Path | • User is logged in with appropriate permissions • Test data is available in the system • Recruitment analytics module is enabled | 1. Navigate to the relevant module/page 2. Verify the feature is accessible 3. Observe the dashboard/display loads 4. Verify data is displayed correctly 5. Test any filters or date range selectors 6. Verify data accuracy against source | **Expected Behavior (Gherkin):** Given the user has appropriate permissions When they access the need to be able to pull list of patients feature Then the feature works as expected **Specific Outcomes:** ✓ Count of consented patients displays accurately ✓ Metrics are segmented by program/channel ✓ Funnel shows progression from invitation to enrollment ✓ Aggregated view available (not patient-level by default) ✓ Data exportable for offline analysis | Must Have | 5-10 min | Validates acceptance criteria for TEST2-RECRUIT-006
TEST2-RECRUIT-057 | TEST2-RECRUIT-006 | RECRUIT | Validate: Count of consented patients displays accurately | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Count of consented patients displays accurately 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Count of consented patients displays accurately | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-006
TEST2-RECRUIT-058 | TEST2-RECRUIT-006 | RECRUIT | Validate: Metrics are segmented by program/channel | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Metrics are segmented by program/channel 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Metrics are segmented by program/channel | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-006
TEST2-RECRUIT-059 | TEST2-RECRUIT-006 | RECRUIT | Validate: Funnel shows progression from invitation to enrollment | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Funnel shows progression from invitation to enrollment 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Funnel shows progression from invitation to enrollment | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-006
TEST2-RECRUIT-060 | TEST2-RECRUIT-006 | RECRUIT | Validate: Aggregated view available (not patient-level by default) | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Aggregated view available (not patient-level by default) 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Aggregated view available (not patient-level by default) | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-006
TEST2-RECRUIT-061 | TEST2-RECRUIT-006 | RECRUIT | Validate: Data exportable for offline analysis | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Data exportable for offline analysis 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Data exportable for offline analysis | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-006
TEST2-RECRUIT-062 | TEST2-RECRUIT-006 | RECRUIT | Verify behavior with insufficient permissions | Negative | • User is logged in | 1. Log in as user without required permissions 2. Attempt to access the feature 3. Observe system response | **Given** a user without permissions **When** they attempt to access the feature **Then** access is denied with appropriate message | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-006
TEST2-RECRUIT-063 | TEST2-RECRUIT-006 | RECRUIT | Verify dashboard with no data | Negative | • User is logged in | 1. Access dashboard with empty dataset 2. Observe display behavior | **Then** empty state message is displayed **And** no errors occur | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-006
TEST2-RECRUIT-064 | TEST2-RECRUIT-006 | RECRUIT | Verify behavior with invalid/malformed input | Negative | • User is logged in | 1. Enter invalid data in required fields 2. Attempt to submit/save 3. Observe validation messages | **Given** invalid input is provided **When** the user submits **Then** clear validation errors are displayed **And** data is not saved | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-006
TEST2-RECRUIT-065 | TEST2-RECRUIT-006 | RECRUIT | Verify with large dataset (10,000+ records) | Edge Case | • User is logged in | 1. Load dashboard with 10,000+ records 2. Observe load time and performance 3. Test pagination/scrolling | **Then** data loads within acceptable time (<10s) **And** pagination works correctly **And** no performance degradation | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-006
TEST2-RECRUIT-066 | TEST2-RECRUIT-006 | RECRUIT | Verify with extreme date range | Edge Case | • User is logged in | 1. Select date range spanning multiple years 2. Observe data aggregation | **Then** data aggregates correctly **And** display remains readable | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-006
TEST2-RECRUIT-067 | TEST2-RECRUIT-007 | RECRUIT | Verify Time on Consent Form | Happy Path | • User is logged in with appropriate permissions • Test data is available in the system • Recruitment analytics module is enabled | 1. Navigate to the relevant module/page 2. Verify the feature is accessible 3. Observe the dashboard/display loads 4. Verify data is displayed correctly 5. Test any filters or date range selectors 6. Verify data accuracy against source | **Expected Behavior (Gherkin):** Given the user has appropriate permissions When they access the track amount of time spent on each conse feature Then the feature works as expected **Specific Outcomes:** ✓ Count of patients patients displays accurately ✓ Metrics are segmented by program/channel ✓ Funnel shows progression from invitation to enrollment ✓ Aggregated view available (not patient-level by default) ✓ Data exportable for offline analysis | Should Have | 5-10 min | Validates acceptance criteria for TEST2-RECRUIT-007
TEST2-RECRUIT-068 | TEST2-RECRUIT-007 | RECRUIT | Validate: Count of patients patients displays accurately | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Count of patients patients displays accurately 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Count of patients patients displays accurately | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-007
TEST2-RECRUIT-069 | TEST2-RECRUIT-007 | RECRUIT | Validate: Metrics are segmented by program/channel | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Metrics are segmented by program/channel 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Metrics are segmented by program/channel | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-007
TEST2-RECRUIT-070 | TEST2-RECRUIT-007 | RECRUIT | Validate: Funnel shows progression from invitation to enrollment | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Funnel shows progression from invitation to enrollment 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Funnel shows progression from invitation to enrollment | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-007
TEST2-RECRUIT-071 | TEST2-RECRUIT-007 | RECRUIT | Validate: Aggregated view available (not patient-level by default) | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Aggregated view available (not patient-level by default) 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Aggregated view available (not patient-level by default) | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-007
TEST2-RECRUIT-072 | TEST2-RECRUIT-007 | RECRUIT | Validate: Data exportable for offline analysis | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Data exportable for offline analysis 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Data exportable for offline analysis | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-007
TEST2-RECRUIT-073 | TEST2-RECRUIT-007 | RECRUIT | Verify behavior with insufficient permissions | Negative | • User is logged in | 1. Log in as user without required permissions 2. Attempt to access the feature 3. Observe system response | **Given** a user without permissions **When** they attempt to access the feature **Then** access is denied with appropriate message | Should Have | 3-5 min | Negative test for TEST2-RECRUIT-007
TEST2-RECRUIT-074 | TEST2-RECRUIT-007 | RECRUIT | Verify dashboard with no data | Negative | • User is logged in | 1. Access dashboard with empty dataset 2. Observe display behavior | **Then** empty state message is displayed **And** no errors occur | Should Have | 3-5 min | Negative test for TEST2-RECRUIT-007
TEST2-RECRUIT-075 | TEST2-RECRUIT-007 | RECRUIT | Verify behavior with invalid/malformed input | Negative | • User is logged in | 1. Enter invalid data in required fields 2. Attempt to submit/save 3. Observe validation messages | **Given** invalid input is provided **When** the user submits **Then** clear validation errors are displayed **And** data is not saved | Should Have | 3-5 min | Negative test for TEST2-RECRUIT-007
TEST2-RECRUIT-076 | TEST2-RECRUIT-007 | RECRUIT | Verify with large dataset (10,000+ records) | Edge Case | • User is logged in | 1. Load dashboard with 10,000+ records 2. Observe load time and performance 3. Test pagination/scrolling | **Then** data loads within acceptable time (<10s) **And** pagination works correctly **And** no performance degradation | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-007
TEST2-RECRUIT-077 | TEST2-RECRUIT-007 | RECRUIT | Verify with extreme date range | Edge Case | • User is logged in | 1. Select date range spanning multiple years 2. Observe data aggregation | **Then** data aggregates correctly **And** display remains readable | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-007
TEST2-RECRUIT-078 | TEST2-RECRUIT-008 | RECRUIT | Verify Saliva Kit Ordering | Happy Path | • User is logged in with appropriate permissions • Test data is available in the system • Recruitment analytics module is enabled | 1. Navigate to the relevant module/page 2. Verify the feature is accessible 3. Observe the dashboard/display loads 4. Verify data is displayed correctly 5. Test any filters or date range selectors 6. Verify data accuracy against source | **Expected Behavior (Gherkin):** Given the user has appropriate permissions When they access the enables Discover Research team to order feature Then the feature works as expected **Specific Outcomes:** ✓ Count of patients patients displays accurately ✓ Metrics are segmented by program/channel ✓ Funnel shows progression from invitation to enrollment ✓ Aggregated view available (not patient-level by default) ✓ Data exportable for offline analysis | Should Have | 5-10 min | Validates acceptance criteria for TEST2-RECRUIT-008
TEST2-RECRUIT-079 | TEST2-RECRUIT-008 | RECRUIT | Validate: Count of patients patients displays accurately | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Count of patients patients displays accurately 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Count of patients patients displays accurately | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-008
TEST2-RECRUIT-080 | TEST2-RECRUIT-008 | RECRUIT | Validate: Metrics are segmented by program/channel | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Metrics are segmented by program/channel 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Metrics are segmented by program/channel | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-008
TEST2-RECRUIT-081 | TEST2-RECRUIT-008 | RECRUIT | Validate: Funnel shows progression from invitation to enrollment | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Funnel shows progression from invitation to enrollment 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Funnel shows progression from invitation to enrollment | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-008
TEST2-RECRUIT-082 | TEST2-RECRUIT-008 | RECRUIT | Validate: Aggregated view available (not patient-level by default) | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Aggregated view available (not patient-level by default) 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Aggregated view available (not patient-level by default) | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-008
TEST2-RECRUIT-083 | TEST2-RECRUIT-008 | RECRUIT | Validate: Data exportable for offline analysis | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Data exportable for offline analysis 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Data exportable for offline analysis | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-008
TEST2-RECRUIT-084 | TEST2-RECRUIT-008 | RECRUIT | Verify behavior with insufficient permissions | Negative | • User is logged in | 1. Log in as user without required permissions 2. Attempt to access the feature 3. Observe system response | **Given** a user without permissions **When** they attempt to access the feature **Then** access is denied with appropriate message | Should Have | 3-5 min | Negative test for TEST2-RECRUIT-008
TEST2-RECRUIT-085 | TEST2-RECRUIT-008 | RECRUIT | Verify dashboard with no data | Negative | • User is logged in | 1. Access dashboard with empty dataset 2. Observe display behavior | **Then** empty state message is displayed **And** no errors occur | Should Have | 3-5 min | Negative test for TEST2-RECRUIT-008
TEST2-RECRUIT-086 | TEST2-RECRUIT-008 | RECRUIT | Verify behavior with invalid/malformed input | Negative | • User is logged in | 1. Enter invalid data in required fields 2. Attempt to submit/save 3. Observe validation messages | **Given** invalid input is provided **When** the user submits **Then** clear validation errors are displayed **And** data is not saved | Should Have | 3-5 min | Negative test for TEST2-RECRUIT-008
TEST2-RECRUIT-087 | TEST2-RECRUIT-008 | RECRUIT | Verify with large dataset (10,000+ records) | Edge Case | • User is logged in | 1. Load dashboard with 10,000+ records 2. Observe load time and performance 3. Test pagination/scrolling | **Then** data loads within acceptable time (<10s) **And** pagination works correctly **And** no performance degradation | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-008
TEST2-RECRUIT-088 | TEST2-RECRUIT-008 | RECRUIT | Verify with extreme date range | Edge Case | • User is logged in | 1. Select date range spanning multiple years 2. Observe data aggregation | **Then** data aggregates correctly **And** display remains readable | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-008
TEST2-RECRUIT-089 | TEST2-RECRUIT-009 | RECRUIT | Verify MyChart Recruitment Cross Validation | Happy Path | • User is logged in with appropriate permissions • Test data is available in the system • Recruitment analytics module is enabled | 1. Navigate to the relevant module/page 2. Verify the feature is accessible 3. Observe the dashboard/display loads 4. Verify data is displayed correctly 5. Test any filters or date range selectors 6. Verify data accuracy against source | **Expected Behavior (Gherkin):** Given the user has appropriate permissions When they access the cross validate participants entering thr feature Then the feature works as expected **Specific Outcomes:** ✓ Count of enrolled patients displays accurately ✓ Metrics are segmented by program/channel ✓ Funnel shows progression from invitation to enrollment ✓ Aggregated view available (not patient-level by default) ✓ Data exportable for offline analysis | Must Have | 5-10 min | Validates acceptance criteria for TEST2-RECRUIT-009
TEST2-RECRUIT-090 | TEST2-RECRUIT-009 | RECRUIT | Validate: Count of enrolled patients displays accurately | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Count of enrolled patients displays accurately 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Count of enrolled patients displays accurately | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-009
TEST2-RECRUIT-091 | TEST2-RECRUIT-009 | RECRUIT | Validate: Metrics are segmented by program/channel | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Metrics are segmented by program/channel 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Metrics are segmented by program/channel | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-009
TEST2-RECRUIT-092 | TEST2-RECRUIT-009 | RECRUIT | Validate: Funnel shows progression from invitation to enrollment | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Funnel shows progression from invitation to enrollment 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Funnel shows progression from invitation to enrollment | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-009
TEST2-RECRUIT-093 | TEST2-RECRUIT-009 | RECRUIT | Validate: Aggregated view available (not patient-level by default) | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Aggregated view available (not patient-level by default) 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Aggregated view available (not patient-level by default) | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-009
TEST2-RECRUIT-094 | TEST2-RECRUIT-009 | RECRUIT | Validate: Data exportable for offline analysis | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Data exportable for offline analysis 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Data exportable for offline analysis | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-009
TEST2-RECRUIT-095 | TEST2-RECRUIT-009 | RECRUIT | Verify behavior with insufficient permissions | Negative | • User is logged in | 1. Log in as user without required permissions 2. Attempt to access the feature 3. Observe system response | **Given** a user without permissions **When** they attempt to access the feature **Then** access is denied with appropriate message | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-009
TEST2-RECRUIT-096 | TEST2-RECRUIT-009 | RECRUIT | Verify dashboard with no data | Negative | • User is logged in | 1. Access dashboard with empty dataset 2. Observe display behavior | **Then** empty state message is displayed **And** no errors occur | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-009
TEST2-RECRUIT-097 | TEST2-RECRUIT-009 | RECRUIT | Verify behavior with invalid/malformed input | Negative | • User is logged in | 1. Enter invalid data in required fields 2. Attempt to submit/save 3. Observe validation messages | **Given** invalid input is provided **When** the user submits **Then** clear validation errors are displayed **And** data is not saved | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-009
TEST2-RECRUIT-098 | TEST2-RECRUIT-009 | RECRUIT | Verify with large dataset (10,000+ records) | Edge Case | • User is logged in | 1. Load dashboard with 10,000+ records 2. Observe load time and performance 3. Test pagination/scrolling | **Then** data loads within acceptable time (<10s) **And** pagination works correctly **And** no performance degradation | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-009
TEST2-RECRUIT-099 | TEST2-RECRUIT-009 | RECRUIT | Verify with extreme date range | Edge Case | • User is logged in | 1. Select date range spanning multiple years 2. Observe data aggregation | **Then** data aggregates correctly **And** display remains readable | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-009
TEST2-RECRUIT-100 | TEST2-RECRUIT-010 | RECRUIT | Verify Multi-Study Dashboard | Happy Path | • User is logged in with appropriate permissions • Test data is available in the system • Recruitment analytics module is enabled | 1. Navigate to the relevant module/page 2. Verify the feature is accessible 3. Observe the dashboard/display loads 4. Verify data is displayed correctly 5. Test any filters or date range selectors 6. Verify data accuracy against source | **Expected Behavior (Gherkin):** Given the user has appropriate permissions When they access the show a personalized list of available st feature Then the feature works as expected **Specific Outcomes:** ✓ Count of enrolled patients displays accurately ✓ Metrics are segmented by program/channel ✓ Funnel shows progression from invitation to enrollment ✓ Aggregated view available (not patient-level by default) ✓ Data exportable for offline analysis | Should Have | 5-10 min | Validates acceptance criteria for TEST2-RECRUIT-010
TEST2-RECRUIT-101 | TEST2-RECRUIT-010 | RECRUIT | Validate: Count of enrolled patients displays accurately | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Count of enrolled patients displays accurately 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Count of enrolled patients displays accurately | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-010
TEST2-RECRUIT-102 | TEST2-RECRUIT-010 | RECRUIT | Validate: Metrics are segmented by program/channel | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Metrics are segmented by program/channel 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Metrics are segmented by program/channel | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-010
TEST2-RECRUIT-103 | TEST2-RECRUIT-010 | RECRUIT | Validate: Funnel shows progression from invitation to enrollment | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Funnel shows progression from invitation to enrollment 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Funnel shows progression from invitation to enrollment | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-010
TEST2-RECRUIT-104 | TEST2-RECRUIT-010 | RECRUIT | Validate: Aggregated view available (not patient-level by default) | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Aggregated view available (not patient-level by default) 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Aggregated view available (not patient-level by default) | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-010
TEST2-RECRUIT-105 | TEST2-RECRUIT-010 | RECRUIT | Validate: Data exportable for offline analysis | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Data exportable for offline analysis 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Data exportable for offline analysis | Should Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-010
TEST2-RECRUIT-106 | TEST2-RECRUIT-010 | RECRUIT | Verify behavior with insufficient permissions | Negative | • User is logged in | 1. Log in as user without required permissions 2. Attempt to access the feature 3. Observe system response | **Given** a user without permissions **When** they attempt to access the feature **Then** access is denied with appropriate message | Should Have | 3-5 min | Negative test for TEST2-RECRUIT-010
TEST2-RECRUIT-107 | TEST2-RECRUIT-010 | RECRUIT | Verify dashboard with no data | Negative | • User is logged in | 1. Access dashboard with empty dataset 2. Observe display behavior | **Then** empty state message is displayed **And** no errors occur | Should Have | 3-5 min | Negative test for TEST2-RECRUIT-010
TEST2-RECRUIT-108 | TEST2-RECRUIT-010 | RECRUIT | Verify behavior with invalid/malformed input | Negative | • User is logged in | 1. Enter invalid data in required fields 2. Attempt to submit/save 3. Observe validation messages | **Given** invalid input is provided **When** the user submits **Then** clear validation errors are displayed **And** data is not saved | Should Have | 3-5 min | Negative test for TEST2-RECRUIT-010
TEST2-RECRUIT-109 | TEST2-RECRUIT-010 | RECRUIT | Verify with large dataset (10,000+ records) | Edge Case | • User is logged in | 1. Load dashboard with 10,000+ records 2. Observe load time and performance 3. Test pagination/scrolling | **Then** data loads within acceptable time (<10s) **And** pagination works correctly **And** no performance degradation | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-010
TEST2-RECRUIT-110 | TEST2-RECRUIT-010 | RECRUIT | Verify with extreme date range | Edge Case | • User is logged in | 1. Select date range spanning multiple years 2. Observe data aggregation | **Then** data aggregates correctly **And** display remains readable | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-010
TEST2-RECRUIT-111 | TEST2-RECRUIT-011 | RECRUIT | Verify SMS Outreach Reminders | Happy Path | • User is logged in with appropriate permissions • Test data is available in the system • Recruitment analytics module is enabled | 1. Navigate to the relevant module/page 2. Verify the feature is accessible 3. Observe the dashboard/display loads 4. Verify data is displayed correctly 5. Test any filters or date range selectors 6. Verify data accuracy against source | **Expected Behavior (Gherkin):** Given the user has appropriate permissions When they access the allows for researchers to reach out to p feature Then the feature works as expected **Specific Outcomes:** ✓ Count of patients patients displays accurately ✓ Metrics are segmented by program/channel ✓ Funnel shows progression from invitation to enrollment ✓ Aggregated view available (not patient-level by default) ✓ Data exportable for offline analysis | Must Have | 5-10 min | Validates acceptance criteria for TEST2-RECRUIT-011
TEST2-RECRUIT-112 | TEST2-RECRUIT-011 | RECRUIT | Validate: Count of patients patients displays accurately | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Count of patients patients displays accurately 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Count of patients patients displays accurately | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-011
TEST2-RECRUIT-113 | TEST2-RECRUIT-011 | RECRUIT | Validate: Metrics are segmented by program/channel | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Metrics are segmented by program/channel 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Metrics are segmented by program/channel | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-011
TEST2-RECRUIT-114 | TEST2-RECRUIT-011 | RECRUIT | Validate: Funnel shows progression from invitation to enrollment | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Funnel shows progression from invitation to enrollment 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Funnel shows progression from invitation to enrollment | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-011
TEST2-RECRUIT-115 | TEST2-RECRUIT-011 | RECRUIT | Validate: Aggregated view available (not patient-level by default) | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Aggregated view available (not patient-level by default) 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Aggregated view available (not patient-level by default) | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-011
TEST2-RECRUIT-116 | TEST2-RECRUIT-011 | RECRUIT | Validate: Data exportable for offline analysis | Validation | • User is logged in • Feature is accessible | 1. Navigate to the relevant feature 2. Verify: Data exportable for offline analysis 3. Document actual behavior 4. Compare to expected behavior | **Given** the feature is accessible **When** the validation is performed **Then** Data exportable for offline analysis | Must Have | 3-5 min | Validates specific acceptance criterion from TEST2-RECRUIT-011
TEST2-RECRUIT-117 | TEST2-RECRUIT-011 | RECRUIT | Verify behavior with insufficient permissions | Negative | • User is logged in | 1. Log in as user without required permissions 2. Attempt to access the feature 3. Observe system response | **Given** a user without permissions **When** they attempt to access the feature **Then** access is denied with appropriate message | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-011
TEST2-RECRUIT-118 | TEST2-RECRUIT-011 | RECRUIT | Verify dashboard with no data | Negative | • User is logged in | 1. Access dashboard with empty dataset 2. Observe display behavior | **Then** empty state message is displayed **And** no errors occur | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-011
TEST2-RECRUIT-119 | TEST2-RECRUIT-011 | RECRUIT | Verify behavior with invalid/malformed input | Negative | • User is logged in | 1. Enter invalid data in required fields 2. Attempt to submit/save 3. Observe validation messages | **Given** invalid input is provided **When** the user submits **Then** clear validation errors are displayed **And** data is not saved | Must Have | 3-5 min | Negative test for TEST2-RECRUIT-011
TEST2-RECRUIT-120 | TEST2-RECRUIT-011 | RECRUIT | Verify with large dataset (10,000+ records) | Edge Case | • User is logged in | 1. Load dashboard with 10,000+ records 2. Observe load time and performance 3. Test pagination/scrolling | **Then** data loads within acceptable time (<10s) **And** pagination works correctly **And** no performance degradation | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-011
TEST2-RECRUIT-121 | TEST2-RECRUIT-011 | RECRUIT | Verify with extreme date range | Edge Case | • User is logged in | 1. Select date range spanning multiple years 2. Observe data aggregation | **Then** data aggregates correctly **And** display remains readable | Could Have | 5-10 min | Edge case test for TEST2-RECRUIT-011
TEST2-P11-AUDI-001 | Reviewed Option C, okay to proceed once final confirmation is received on viability. For 3a, can you clarify if through assessment/appropriate channel means that the patient would be linked to where they left off after completing their clinical program assessment (I.e., they get to the accordion to see the intro about Discover and navigate away/close the window and then receive a reminder.) | Part 11 - Audit Trail | Verify audit log captures user identity for data modification | Happy Path | • Test user account exists • User is logged in with known identity • Audit logging is enabled | 1. Log in as test user (test_user) 2. Perform data modification on a record 3. Navigate to audit log / history 4. Locate the audit entry for the action | • Audit entry exists for the action • User identity (username/ID) is recorded • User identity matches logged-in user | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-002 | Reviewed Option C, okay to proceed once final confirmation is received on viability. For 3a, can you clarify if through assessment/appropriate channel means that the patient would be linked to where they left off after completing their clinical program assessment (I.e., they get to the accordion to see the intro about Discover and navigate away/close the window and then receive a reminder.) | Part 11 - Audit Trail | Verify audit log captures timestamp for data modification | Happy Path | • System clock is synchronized • User is logged in | 1. Note the current date/time 2. Perform data modification on a record 3. View audit log entry for the action 4. Compare timestamp to noted time | • Timestamp is recorded in audit entry • Timestamp is within acceptable tolerance of action time • Timestamp includes date, time, and timezone | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-003 | Reviewed Option C, okay to proceed once final confirmation is received on viability. For 3a, can you clarify if through assessment/appropriate channel means that the patient would be linked to where they left off after completing their clinical program assessment (I.e., they get to the accordion to see the intro about Discover and navigate away/close the window and then receive a reminder.) | Part 11 - Audit Trail | Verify audit log captures before/after values for data modification | Happy Path | • Record exists with known field values • User has permission to modify record | 1. Note current value of field to be changed 2. Modify the field value 3. View audit log entry 4. Verify before and after values are recorded | • Previous (before) value is recorded • New (after) value is recorded • Both values are accurate | Must Have | 7 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-004 | Reviewed Option C, okay to proceed once final confirmation is received on viability. For 3a, can you clarify if through assessment/appropriate channel means that the patient would be linked to where they left off after completing their clinical program assessment (I.e., they get to the accordion to see the intro about Discover and navigate away/close the window and then receive a reminder.) | Part 11 - Audit Trail | Verify audit records cannot be modified or deleted | Negative | • Audit records exist in system • User with highest privileges is logged in | 1. Log in as administrator/highest privilege user 2. Navigate to audit log 3. Attempt to edit an audit record 4. Attempt to delete an audit record | • No option to edit audit records exists • No option to delete audit records exists • If attempted via other means, action is blocked | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-005 | Reviewed requirements and no further notes. Okay to move forward. | Part 11 - Audit Trail | Verify audit log captures user identity for data modification | Happy Path | • Test user account exists • User is logged in with known identity • Audit logging is enabled | 1. Log in as test user (test_user) 2. Perform data modification on a record 3. Navigate to audit log / history 4. Locate the audit entry for the action | • Audit entry exists for the action • User identity (username/ID) is recorded • User identity matches logged-in user | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-006 | Reviewed requirements and no further notes. Okay to move forward. | Part 11 - Audit Trail | Verify audit log captures timestamp for data modification | Happy Path | • System clock is synchronized • User is logged in | 1. Note the current date/time 2. Perform data modification on a record 3. View audit log entry for the action 4. Compare timestamp to noted time | • Timestamp is recorded in audit entry • Timestamp is within acceptable tolerance of action time • Timestamp includes date, time, and timezone | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-007 | Reviewed requirements and no further notes. Okay to move forward. | Part 11 - Audit Trail | Verify audit log captures before/after values for data modification | Happy Path | • Record exists with known field values • User has permission to modify record | 1. Note current value of field to be changed 2. Modify the field value 3. View audit log entry 4. Verify before and after values are recorded | • Previous (before) value is recorded • New (after) value is recorded • Both values are accurate | Must Have | 7 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-008 | Reviewed requirements and no further notes. Okay to move forward. | Part 11 - Audit Trail | Verify audit records cannot be modified or deleted | Negative | • Audit records exist in system • User with highest privileges is logged in | 1. Log in as administrator/highest privilege user 2. Navigate to audit log 3. Attempt to edit an audit record 4. Attempt to delete an audit record | • No option to edit audit records exists • No option to delete audit records exists • If attempted via other means, action is blocked | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-009 |  | Part 11 - Audit Trail | Verify audit log captures user identity for data modification | Happy Path | • Test user account exists • User is logged in with known identity • Audit logging is enabled | 1. Log in as test user (test_user) 2. Perform data modification on a record 3. Navigate to audit log / history 4. Locate the audit entry for the action | • Audit entry exists for the action • User identity (username/ID) is recorded • User identity matches logged-in user | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-010 |  | Part 11 - Audit Trail | Verify audit log captures timestamp for data modification | Happy Path | • System clock is synchronized • User is logged in | 1. Note the current date/time 2. Perform data modification on a record 3. View audit log entry for the action 4. Compare timestamp to noted time | • Timestamp is recorded in audit entry • Timestamp is within acceptable tolerance of action time • Timestamp includes date, time, and timezone | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-011 |  | Part 11 - Audit Trail | Verify audit log captures before/after values for data modification | Happy Path | • Record exists with known field values • User has permission to modify record | 1. Note current value of field to be changed 2. Modify the field value 3. View audit log entry 4. Verify before and after values are recorded | • Previous (before) value is recorded • New (after) value is recorded • Both values are accurate | Must Have | 7 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-012 |  | Part 11 - Audit Trail | Verify audit records cannot be modified or deleted | Negative | • Audit records exist in system • User with highest privileges is logged in | 1. Log in as administrator/highest privilege user 2. Navigate to audit log 3. Attempt to edit an audit record 4. Attempt to delete an audit record | • No option to edit audit records exists • No option to delete audit records exists • If attempted via other means, action is blocked | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-013 |  | Part 11 - Audit Trail | Verify audit log captures user identity for data modification | Happy Path | • Test user account exists • User is logged in with known identity • Audit logging is enabled | 1. Log in as test user (test_user) 2. Perform data modification on a record 3. Navigate to audit log / history 4. Locate the audit entry for the action | • Audit entry exists for the action • User identity (username/ID) is recorded • User identity matches logged-in user | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-014 |  | Part 11 - Audit Trail | Verify audit log captures timestamp for data modification | Happy Path | • System clock is synchronized • User is logged in | 1. Note the current date/time 2. Perform data modification on a record 3. View audit log entry for the action 4. Compare timestamp to noted time | • Timestamp is recorded in audit entry • Timestamp is within acceptable tolerance of action time • Timestamp includes date, time, and timezone | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-015 |  | Part 11 - Audit Trail | Verify audit log captures before/after values for data modification | Happy Path | • Record exists with known field values • User has permission to modify record | 1. Note current value of field to be changed 2. Modify the field value 3. View audit log entry 4. Verify before and after values are recorded | • Previous (before) value is recorded • New (after) value is recorded • Both values are accurate | Must Have | 7 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-016 |  | Part 11 - Audit Trail | Verify audit records cannot be modified or deleted | Negative | • Audit records exist in system • User with highest privileges is logged in | 1. Log in as administrator/highest privilege user 2. Navigate to audit log 3. Attempt to edit an audit record 4. Attempt to delete an audit record | • No option to edit audit records exists • No option to delete audit records exists • If attempted via other means, action is blocked | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-017 |  | Part 11 - Audit Trail | Verify audit log captures user identity for enter | Happy Path | • Test user account exists • User is logged in with known identity • Audit logging is enabled | 1. Log in as test user (test_user) 2. Perform enter on a record 3. Navigate to audit log / history 4. Locate the audit entry for the action | • Audit entry exists for the action • User identity (username/ID) is recorded • User identity matches logged-in user | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-018 |  | Part 11 - Audit Trail | Verify audit log captures timestamp for enter | Happy Path | • System clock is synchronized • User is logged in | 1. Note the current date/time 2. Perform enter on a record 3. View audit log entry for the action 4. Compare timestamp to noted time | • Timestamp is recorded in audit entry • Timestamp is within acceptable tolerance of action time • Timestamp includes date, time, and timezone | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-019 |  | Part 11 - Audit Trail | Verify audit log captures before/after values for enter | Happy Path | • Record exists with known field values • User has permission to modify record | 1. Note current value of field to be changed 2. Modify the field value 3. View audit log entry 4. Verify before and after values are recorded | • Previous (before) value is recorded • New (after) value is recorded • Both values are accurate | Must Have | 7 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-020 |  | Part 11 - Audit Trail | Verify audit records cannot be modified or deleted | Negative | • Audit records exist in system • User with highest privileges is logged in | 1. Log in as administrator/highest privilege user 2. Navigate to audit log 3. Attempt to edit an audit record 4. Attempt to delete an audit record | • No option to edit audit records exists • No option to delete audit records exists • If attempted via other means, action is blocked | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-ELEC-001 |  | Part 11 - E-Signature | Verify e-signature displays signer name for enter | Happy Path | • Document/record ready for signature • User authorized to sign | 1. Navigate to document requiring signature 2. Initiate signature process 3. Complete authentication 4. Apply signature 5. View signed document | • Signer printed name is displayed • Name matches authenticated user • Name is human-readable (not just ID) | Must Have | 5 min | Part 11 compliance test for electronic signature
TEST2-P11-ELEC-002 |  | Part 11 - E-Signature | Verify e-signature includes date and time | Happy Path | • Document ready for signature • System clock is accurate | 1. Note current date and time 2. Apply signature to document 3. View signature details 4. Compare signature timestamp to noted time | • Date is displayed with signature • Time is displayed with signature • Timestamp is accurate to within acceptable tolerance | Must Have | 5 min | Part 11 compliance test for electronic signature
TEST2-P11-ELEC-003 |  | Part 11 - E-Signature | Verify e-signature includes meaning/purpose | Happy Path | • Document requiring specific approval type exists | 1. Navigate to document for approval 2. Apply signature 3. View signature manifestation 4. Verify meaning is displayed | • Signature meaning is displayed (e.g., "Approved", "Reviewed") • Meaning accurately reflects signature purpose • Meaning cannot be changed after signing | Must Have | 5 min | Part 11 compliance test for electronic signature
TEST2-P11-ELEC-004 |  | Part 11 - E-Signature | Verify signature requires authentication | Happy Path | • User is logged in • Document ready for signature | 1. Navigate to document requiring signature 2. Click sign/approve button 3. Observe authentication prompt 4. Enter credentials 5. Complete signature | • System prompts for authentication before signing • Password or other credential required • Signature not applied without authentication | Must Have | 5 min | Part 11 compliance test for electronic signature
TEST2-P11-ELEC-005 |  | Part 11 - E-Signature | Verify signature fails with incorrect credentials | Negative | • User is logged in • Document ready for signature | 1. Navigate to document requiring signature 2. Initiate signature 3. Enter incorrect password 4. Attempt to complete signature | • Signature is NOT applied • Error message displayed • User may retry with correct credentials | Must Have | 5 min | Part 11 compliance test for electronic signature
TEST2-P11-DATA-001 |  | Part 11 - Data Integrity | Verify data validation on input for data field | Negative | • Form with validated fields exists • Validation rules are known | 1. Navigate to data entry form 2. Enter invalid data in data field 3. Attempt to save/submit 4. Observe validation response | • Invalid data is rejected • Clear error message displayed • Form indicates which field failed validation • Invalid data is not saved | Must Have | 5 min | Part 11 compliance test for data integrity
TEST2-P11-DATA-002 |  | Part 11 - Data Integrity | Verify required fields cannot be bypassed | Negative | • Form with required fields exists | 1. Navigate to data entry form 2. Leave required field blank 3. Attempt to save/submit 4. Observe system response | • Submission is prevented • Required field is highlighted • Clear message indicates required fields | Must Have | 5 min | Part 11 compliance test for data integrity
TEST2-P11-ELEC-006 |  | Part 11 - E-Signature | Verify e-signature displays signer name for sign | Happy Path | • Document/record ready for signature • User authorized to sign | 1. Navigate to document requiring signature 2. Initiate signature process 3. Complete authentication 4. Apply signature 5. View signed document | • Signer printed name is displayed • Name matches authenticated user • Name is human-readable (not just ID) | Must Have | 5 min | Part 11 compliance test for electronic signature
TEST2-P11-ELEC-007 |  | Part 11 - E-Signature | Verify e-signature includes date and time | Happy Path | • Document ready for signature • System clock is accurate | 1. Note current date and time 2. Apply signature to document 3. View signature details 4. Compare signature timestamp to noted time | • Date is displayed with signature • Time is displayed with signature • Timestamp is accurate to within acceptable tolerance | Must Have | 5 min | Part 11 compliance test for electronic signature
TEST2-P11-ELEC-008 |  | Part 11 - E-Signature | Verify e-signature includes meaning/purpose | Happy Path | • Document requiring specific approval type exists | 1. Navigate to document for approval 2. Apply signature 3. View signature manifestation 4. Verify meaning is displayed | • Signature meaning is displayed (e.g., "Approved", "Reviewed") • Meaning accurately reflects signature purpose • Meaning cannot be changed after signing | Must Have | 5 min | Part 11 compliance test for electronic signature
TEST2-P11-ELEC-009 |  | Part 11 - E-Signature | Verify signature requires authentication | Happy Path | • User is logged in • Document ready for signature | 1. Navigate to document requiring signature 2. Click sign/approve button 3. Observe authentication prompt 4. Enter credentials 5. Complete signature | • System prompts for authentication before signing • Password or other credential required • Signature not applied without authentication | Must Have | 5 min | Part 11 compliance test for electronic signature
TEST2-P11-ELEC-010 |  | Part 11 - E-Signature | Verify signature fails with incorrect credentials | Negative | • User is logged in • Document ready for signature | 1. Navigate to document requiring signature 2. Initiate signature 3. Enter incorrect password 4. Attempt to complete signature | • Signature is NOT applied • Error message displayed • User may retry with correct credentials | Must Have | 5 min | Part 11 compliance test for electronic signature
TEST2-P11-AUDI-021 | Nick to reach out to Andrew for template. Draft language in process with Discover Team. | Part 11 - Audit Trail | Verify audit log captures user identity for data modification | Happy Path | • Test user account exists • User is logged in with known identity • Audit logging is enabled | 1. Log in as test user (test_user) 2. Perform data modification on a record 3. Navigate to audit log / history 4. Locate the audit entry for the action | • Audit entry exists for the action • User identity (username/ID) is recorded • User identity matches logged-in user | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-022 | Nick to reach out to Andrew for template. Draft language in process with Discover Team. | Part 11 - Audit Trail | Verify audit log captures timestamp for data modification | Happy Path | • System clock is synchronized • User is logged in | 1. Note the current date/time 2. Perform data modification on a record 3. View audit log entry for the action 4. Compare timestamp to noted time | • Timestamp is recorded in audit entry • Timestamp is within acceptable tolerance of action time • Timestamp includes date, time, and timezone | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-023 | Nick to reach out to Andrew for template. Draft language in process with Discover Team. | Part 11 - Audit Trail | Verify audit log captures before/after values for data modification | Happy Path | • Record exists with known field values • User has permission to modify record | 1. Note current value of field to be changed 2. Modify the field value 3. View audit log entry 4. Verify before and after values are recorded | • Previous (before) value is recorded • New (after) value is recorded • Both values are accurate | Must Have | 7 min | Part 11 compliance test for audit trail
TEST2-P11-AUDI-024 | Nick to reach out to Andrew for template. Draft language in process with Discover Team. | Part 11 - Audit Trail | Verify audit records cannot be modified or deleted | Negative | • Audit records exist in system • User with highest privileges is logged in | 1. Log in as administrator/highest privilege user 2. Navigate to audit log 3. Attempt to edit an audit record 4. Attempt to delete an audit record | • No option to edit audit records exists • No option to delete audit records exists • If attempted via other means, action is blocked | Must Have | 5 min | Part 11 compliance test for audit trail
TEST2-HIPAA-PHI_-001 | Reviewed Option C, okay to proceed once final confirmation is received on viability. For 3a, can you clarify if through assessment/appropriate channel means that the patient would be linked to where they left off after completing their clinical program assessment (I.e., they get to the accordion to see the intro about Discover and navigate away/close the window and then receive a reminder.) | HIPAA - PHI Handling | Verify PHI can be securely updated in patient records | Happy Path | • User with PHI edit permission • Existing PHI record | 1. Log in as authorized user 2. Navigate to PHI record 3. Update PHI field 4. Save changes | • PHI update successful • Previous value retained in history • Update logged in audit trail • Change transmitted securely | Must Have | 7 min | HIPAA compliance test for phi handling
TEST2-HIPAA-PHI_-002 | Reviewed Option C, okay to proceed once final confirmation is received on viability. For 3a, can you clarify if through assessment/appropriate channel means that the patient would be linked to where they left off after completing their clinical program assessment (I.e., they get to the accordion to see the intro about Discover and navigate away/close the window and then receive a reminder.) | HIPAA - PHI Handling | Verify PHI export includes only authorized data | Happy Path | • Export function exists • User with export permission | 1. Select records for export 2. Initiate export 3. Review exported data | • Export contains only authorized PHI • Export is logged • Export file is encrypted or password-protected | Should Have | 10 min | HIPAA compliance test for phi handling
TEST2-HIPAA-ENCR-001 | Reviewed Option C, okay to proceed once final confirmation is received on viability. For 3a, can you clarify if through assessment/appropriate channel means that the patient would be linked to where they left off after completing their clinical program assessment (I.e., they get to the accordion to see the intro about Discover and navigate away/close the window and then receive a reminder.) | HIPAA - Encryption | Verify PHI is encrypted in transit for patient records | Happy Path | • Network monitoring tool available • Test environment configured | 1. Configure network traffic capture 2. Access PHI through patient records 3. Examine captured traffic 4. Verify encryption | • All PHI traffic uses TLS/HTTPS • PHI not visible in plain text • Certificate is valid and trusted | Must Have | 15 min | HIPAA compliance test for encryption
TEST2-HIPAA-ENCR-002 | Reviewed Option C, okay to proceed once final confirmation is received on viability. For 3a, can you clarify if through assessment/appropriate channel means that the patient would be linked to where they left off after completing their clinical program assessment (I.e., they get to the accordion to see the intro about Discover and navigate away/close the window and then receive a reminder.) | HIPAA - Encryption | Verify PHI is encrypted at rest | Happy Path | • Database access available • Encryption configured | 1. Enter PHI through application 2. Access database directly 3. Examine stored PHI 4. Verify encryption | • PHI is not readable in raw database • Encryption keys properly managed • Only application can decrypt | Must Have | 15 min | HIPAA compliance test for encryption
TEST2-HIPAA-ENCR-003 | Reviewed Option C, okay to proceed once final confirmation is received on viability. For 3a, can you clarify if through assessment/appropriate channel means that the patient would be linked to where they left off after completing their clinical program assessment (I.e., they get to the accordion to see the intro about Discover and navigate away/close the window and then receive a reminder.) | HIPAA - Encryption | Verify insecure connection rejected | Negative | • Ability to attempt HTTP connection | 1. Attempt to access patient records via HTTP (not HTTPS) 2. Observe system response | • HTTP connection rejected or redirected to HTTPS • PHI not accessible over unencrypted connection • Security warning displayed if applicable | Must Have | 5 min | HIPAA compliance test for encryption
TEST2-HIPAA-AUDI-001 | Reviewed Option C, okay to proceed once final confirmation is received on viability. For 3a, can you clarify if through assessment/appropriate channel means that the patient would be linked to where they left off after completing their clinical program assessment (I.e., they get to the accordion to see the intro about Discover and navigate away/close the window and then receive a reminder.) | HIPAA - Audit Controls | Verify PHI access is logged for patient records | Happy Path | • Audit logging enabled • User with PHI access | 1. Note current time 2. Access PHI in patient records 3. View audit log 4. Locate access entry | • Access is recorded in audit log • Log includes: user, timestamp, action, PHI accessed • Log entry cannot be modified | Must Have | 7 min | HIPAA compliance test for audit logging
TEST2-HIPAA-AUDI-002 | Reviewed Option C, okay to proceed once final confirmation is received on viability. For 3a, can you clarify if through assessment/appropriate channel means that the patient would be linked to where they left off after completing their clinical program assessment (I.e., they get to the accordion to see the intro about Discover and navigate away/close the window and then receive a reminder.) | HIPAA - Audit Controls | Verify audit log includes required details | Happy Path | • Recent PHI access events exist | 1. Navigate to audit log 2. Select recent PHI access event 3. Review log entry details | • User identity recorded • Date and time recorded • Type of action recorded (view/edit/delete) • Record/patient identifier logged | Must Have | 5 min | HIPAA compliance test for audit logging
TEST2-HIPAA-AUDI-003 | Reviewed Option C, okay to proceed once final confirmation is received on viability. For 3a, can you clarify if through assessment/appropriate channel means that the patient would be linked to where they left off after completing their clinical program assessment (I.e., they get to the accordion to see the intro about Discover and navigate away/close the window and then receive a reminder.) | HIPAA - Audit Controls | Verify failed PHI access attempts are logged | Negative | • User without PHI access | 1. Attempt to access PHI without authorization 2. Access is denied (expected) 3. View audit log 4. Verify failed attempt logged | • Failed access attempt is logged • Log includes user and timestamp • Alerts generated if configured | Must Have | 7 min | HIPAA compliance test for audit logging
TEST2-HIPAA-AUDI-004 | Reviewed Option C, okay to proceed once final confirmation is received on viability. For 3a, can you clarify if through assessment/appropriate channel means that the patient would be linked to where they left off after completing their clinical program assessment (I.e., they get to the accordion to see the intro about Discover and navigate away/close the window and then receive a reminder.) | HIPAA - Audit Controls | Verify audit logs cannot be deleted | Negative | • Admin access to system | 1. Log in as administrator 2. Navigate to audit logs 3. Attempt to delete or modify log entry | • Delete/modify options not available • If attempted, action is blocked • Attempt to tamper is itself logged | Must Have | 5 min | HIPAA compliance test for audit logging
TEST2-HIPAA-PHI_-003 | Reviewed requirements and no further notes. Okay to move forward. | HIPAA - PHI Handling | Verify PHI can be securely updated in patient records | Happy Path | • User with PHI edit permission • Existing PHI record | 1. Log in as authorized user 2. Navigate to PHI record 3. Update PHI field 4. Save changes | • PHI update successful • Previous value retained in history • Update logged in audit trail • Change transmitted securely | Must Have | 7 min | HIPAA compliance test for phi handling
TEST2-HIPAA-PHI_-004 | Reviewed requirements and no further notes. Okay to move forward. | HIPAA - PHI Handling | Verify PHI export includes only authorized data | Happy Path | • Export function exists • User with export permission | 1. Select records for export 2. Initiate export 3. Review exported data | • Export contains only authorized PHI • Export is logged • Export file is encrypted or password-protected | Should Have | 10 min | HIPAA compliance test for phi handling
TEST2-HIPAA-AUDI-005 | Reviewed requirements and no further notes. Okay to move forward. | HIPAA - Audit Controls | Verify PHI access is logged for patient records | Happy Path | • Audit logging enabled • User with PHI access | 1. Note current time 2. Access PHI in patient records 3. View audit log 4. Locate access entry | • Access is recorded in audit log • Log includes: user, timestamp, action, PHI accessed • Log entry cannot be modified | Must Have | 7 min | HIPAA compliance test for audit logging
TEST2-HIPAA-AUDI-006 | Reviewed requirements and no further notes. Okay to move forward. | HIPAA - Audit Controls | Verify audit log includes required details | Happy Path | • Recent PHI access events exist | 1. Navigate to audit log 2. Select recent PHI access event 3. Review log entry details | • User identity recorded • Date and time recorded • Type of action recorded (view/edit/delete) • Record/patient identifier logged | Must Have | 5 min | HIPAA compliance test for audit logging
TEST2-HIPAA-AUDI-007 | Reviewed requirements and no further notes. Okay to move forward. | HIPAA - Audit Controls | Verify failed PHI access attempts are logged | Negative | • User without PHI access | 1. Attempt to access PHI without authorization 2. Access is denied (expected) 3. View audit log 4. Verify failed attempt logged | • Failed access attempt is logged • Log includes user and timestamp • Alerts generated if configured | Must Have | 7 min | HIPAA compliance test for audit logging
TEST2-HIPAA-AUDI-008 | Reviewed requirements and no further notes. Okay to move forward. | HIPAA - Audit Controls | Verify audit logs cannot be deleted | Negative | • Admin access to system | 1. Log in as administrator 2. Navigate to audit logs 3. Attempt to delete or modify log entry | • Delete/modify options not available • If attempted, action is blocked • Attempt to tamper is itself logged | Must Have | 5 min | HIPAA compliance test for audit logging
TEST2-HIPAA-PHI_-005 |  | HIPAA - PHI Handling | Verify PHI can be securely updated in patient records | Happy Path | • User with PHI edit permission • Existing PHI record | 1. Log in as authorized user 2. Navigate to PHI record 3. Update PHI field 4. Save changes | • PHI update successful • Previous value retained in history • Update logged in audit trail • Change transmitted securely | Must Have | 7 min | HIPAA compliance test for phi handling
TEST2-HIPAA-PHI_-006 |  | HIPAA - PHI Handling | Verify PHI export includes only authorized data | Happy Path | • Export function exists • User with export permission | 1. Select records for export 2. Initiate export 3. Review exported data | • Export contains only authorized PHI • Export is logged • Export file is encrypted or password-protected | Should Have | 10 min | HIPAA compliance test for phi handling
TEST2-HIPAA-AUDI-009 |  | HIPAA - Audit Controls | Verify PHI access is logged for patient records | Happy Path | • Audit logging enabled • User with PHI access | 1. Note current time 2. Access PHI in patient records 3. View audit log 4. Locate access entry | • Access is recorded in audit log • Log includes: user, timestamp, action, PHI accessed • Log entry cannot be modified | Must Have | 7 min | HIPAA compliance test for audit logging
TEST2-HIPAA-AUDI-010 |  | HIPAA - Audit Controls | Verify audit log includes required details | Happy Path | • Recent PHI access events exist | 1. Navigate to audit log 2. Select recent PHI access event 3. Review log entry details | • User identity recorded • Date and time recorded • Type of action recorded (view/edit/delete) • Record/patient identifier logged | Must Have | 5 min | HIPAA compliance test for audit logging
TEST2-HIPAA-AUDI-011 |  | HIPAA - Audit Controls | Verify failed PHI access attempts are logged | Negative | • User without PHI access | 1. Attempt to access PHI without authorization 2. Access is denied (expected) 3. View audit log 4. Verify failed attempt logged | • Failed access attempt is logged • Log includes user and timestamp • Alerts generated if configured | Must Have | 7 min | HIPAA compliance test for audit logging
TEST2-HIPAA-AUDI-012 |  | HIPAA - Audit Controls | Verify audit logs cannot be deleted | Negative | • Admin access to system | 1. Log in as administrator 2. Navigate to audit logs 3. Attempt to delete or modify log entry | • Delete/modify options not available • If attempted, action is blocked • Attempt to tamper is itself logged | Must Have | 5 min | HIPAA compliance test for audit logging
TEST2-HIPAA-PHI_-007 |  | HIPAA - PHI Handling | Verify PHI can be securely updated in patient records | Happy Path | • User with PHI edit permission • Existing PHI record | 1. Log in as authorized user 2. Navigate to PHI record 3. Update PHI field 4. Save changes | • PHI update successful • Previous value retained in history • Update logged in audit trail • Change transmitted securely | Must Have | 7 min | HIPAA compliance test for phi handling
TEST2-HIPAA-PHI_-008 |  | HIPAA - PHI Handling | Verify PHI export includes only authorized data | Happy Path | • Export function exists • User with export permission | 1. Select records for export 2. Initiate export 3. Review exported data | • Export contains only authorized PHI • Export is logged • Export file is encrypted or password-protected | Should Have | 10 min | HIPAA compliance test for phi handling
TEST2-HIPAA-PHI_-009 | Nick to reach out to Andrew for template. Draft language in process with Discover Team. | HIPAA - PHI Handling | Verify PHI can be securely updated in patient records | Happy Path | • User with PHI edit permission • Existing PHI record | 1. Log in as authorized user 2. Navigate to PHI record 3. Update PHI field 4. Save changes | • PHI update successful • Previous value retained in history • Update logged in audit trail • Change transmitted securely | Must Have | 7 min | HIPAA compliance test for phi handling
TEST2-HIPAA-PHI_-010 | Nick to reach out to Andrew for template. Draft language in process with Discover Team. | HIPAA - PHI Handling | Verify PHI export includes only authorized data | Happy Path | • Export function exists • User with export permission | 1. Select records for export 2. Initiate export 3. Review exported data | • Export contains only authorized PHI • Export is logged • Export file is encrypted or password-protected | Should Have | 10 min | HIPAA compliance test for phi handling
TEST2-SOC2-PRI-001 |  | SOC 2 - Privacy | Verify privacy notice is displayed | Happy Path | • Privacy notice configured • New user scenario available | 1. Navigate to registration/signup 2. Locate privacy notice link 3. Review privacy notice content 4. Verify completeness | • Privacy notice accessible • Notice is current and complete • Easy to understand • Contact information provided | Should Have | 5 min | SOC 2 Privacy test
TEST2-SOC2-PRI-002 |  | SOC 2 - Privacy | Verify consent collection | Happy Path | • Consent mechanism configured | 1. Navigate to data collection point 2. Verify consent request displayed 3. Provide consent 4. Verify consent recorded | • Consent clearly requested • Options clearly explained • Consent recorded with timestamp • User can review consent status | Must Have | 5 min | SOC 2 Privacy test
TEST2-SOC2-PRI-003 |  | SOC 2 - Privacy | Verify opt-out functionality | Happy Path | • User with active consent • Opt-out mechanism available | 1. Log in as user with consent 2. Navigate to privacy settings 3. Exercise opt-out option 4. Verify opt-out processed | • Opt-out option available • Opt-out confirmation received • Consent status updated • Data processing stopped | Must Have | 7 min | SOC 2 Privacy test
TEST2-SOC2-PRI-004 |  | SOC 2 - Privacy | Verify data deletion request | Happy Path | • Data deletion mechanism available • User data exists | 1. Submit data deletion request 2. Verify request acknowledged 3. Check deletion status 4. Verify data removed | • Request mechanism available • Request acknowledged • Deletion completed within policy timeframe • Confirmation provided | Should Have | 15 min | SOC 2 Privacy test
TEST2-SOC2-PRI-005 |  | SOC 2 - Privacy | Verify data subject access request | Happy Path | • DSAR mechanism available | 1. Submit data access request 2. Verify identity as required 3. Receive data export 4. Verify data completeness | • Access request mechanism available • Identity verification required • Data provided in usable format • All personal data included | Should Have | 15 min | SOC 2 Privacy test
TEST2-SOC2-SEC-001 | Reviewed and okay to proceed with no additional notes. | SOC 2 - Security | Verify role-based access control for user management | Happy Path | • Users with different roles exist • Access permissions configured | 1. Log in as user with specific role 2. Navigate to user management 3. Attempt to perform role-appropriate action 4. Verify action succeeds | • Access granted for authorized actions • Unauthorized actions are blocked • Access logged in audit trail | Must Have | 5 min | SOC 2 Security test
TEST2-SOC2-SEC-002 | Reviewed and okay to proceed with no additional notes. | SOC 2 - Security | Verify unauthorized access is denied for user management | Negative | • User without required permissions exists | 1. Log in as user WITHOUT access to user management 2. Attempt to access user management 3. Observe system response | • Access is denied • Appropriate error message shown • Unauthorized attempt is logged | Must Have | 5 min | SOC 2 Security test
TEST2-SOC2-SEC-003 | Reviewed and okay to proceed with no additional notes. | SOC 2 - Security | Verify MFA is enforced for user management | Happy Path | • MFA is configured • User has MFA enabled | 1. Navigate to login 2. Enter username and password 3. Complete MFA challenge 4. Access user management | • MFA prompt displayed after password • Access granted only after MFA • Failed MFA blocks access | Must Have | 5 min | SOC 2 Security test
TEST2-SOC2-SEC-004 | Reviewed and okay to proceed with no additional notes. | SOC 2 - Security | Verify data encryption in transit | Happy Path | • Network monitoring tool available • Test environment accessible | 1. Configure traffic capture 2. Perform data operation 3. Examine captured traffic 4. Verify TLS/encryption | • All traffic uses HTTPS/TLS • Data not visible in plain text • Valid certificates in use | Must Have | 15 min | SOC 2 Security test
TEST2-SOC2-SEC-005 | Reviewed and okay to proceed with no additional notes. | SOC 2 - Security | Verify security event logging | Happy Path | • Audit logging enabled • Access to security logs | 1. Perform security-relevant action (login, access, etc.) 2. Navigate to security logs 3. Locate event entry 4. Verify log content | • Event logged with timestamp • User identity captured • Action type recorded • Source IP/location logged | Must Have | 7 min | SOC 2 Security test
TEST2-SOC2-SEC-006 | Reviewed and okay to proceed with no additional notes. | SOC 2 - Security | Verify account lockout after failed attempts | Negative | • Account lockout configured • Valid user account | 1. Navigate to login 2. Enter valid username 3. Enter incorrect password (repeat until lockout) 4. Attempt login with correct password | • Account locked after threshold • Login denied even with correct password • Lockout event logged • User notified of lockout | Must Have | 7 min | SOC 2 Security test
TEST2-SOC2-PRI-006 | Reviewed and okay to proceed with no additional notes. | SOC 2 - Privacy | Verify privacy notice is displayed | Happy Path | • Privacy notice configured • New user scenario available | 1. Navigate to registration/signup 2. Locate privacy notice link 3. Review privacy notice content 4. Verify completeness | • Privacy notice accessible • Notice is current and complete • Easy to understand • Contact information provided | Should Have | 5 min | SOC 2 Privacy test
TEST2-SOC2-PRI-007 | Reviewed and okay to proceed with no additional notes. | SOC 2 - Privacy | Verify consent collection | Happy Path | • Consent mechanism configured | 1. Navigate to data collection point 2. Verify consent request displayed 3. Provide consent 4. Verify consent recorded | • Consent clearly requested • Options clearly explained • Consent recorded with timestamp • User can review consent status | Must Have | 5 min | SOC 2 Privacy test
TEST2-SOC2-PRI-008 | Reviewed and okay to proceed with no additional notes. | SOC 2 - Privacy | Verify opt-out functionality | Happy Path | • User with active consent • Opt-out mechanism available | 1. Log in as user with consent 2. Navigate to privacy settings 3. Exercise opt-out option 4. Verify opt-out processed | • Opt-out option available • Opt-out confirmation received • Consent status updated • Data processing stopped | Must Have | 7 min | SOC 2 Privacy test
TEST2-SOC2-PRI-009 | Reviewed and okay to proceed with no additional notes. | SOC 2 - Privacy | Verify data deletion request | Happy Path | • Data deletion mechanism available • User data exists | 1. Submit data deletion request 2. Verify request acknowledged 3. Check deletion status 4. Verify data removed | • Request mechanism available • Request acknowledged • Deletion completed within policy timeframe • Confirmation provided | Should Have | 15 min | SOC 2 Privacy test
TEST2-SOC2-PRI-010 | Reviewed and okay to proceed with no additional notes. | SOC 2 - Privacy | Verify data subject access request | Happy Path | • DSAR mechanism available | 1. Submit data access request 2. Verify identity as required 3. Receive data export 4. Verify data completeness | • Access request mechanism available • Identity verification required • Data provided in usable format • All personal data included | Should Have | 15 min | SOC 2 Privacy test
TEST2-SOC2-PI-001 |  | SOC 2 - Processing Integrity | Verify input validation for application | Negative | • Data entry form available • Validation rules known | 1. Navigate to application form 2. Enter invalid data 3. Attempt to submit 4. Observe validation response | • Invalid data rejected • Clear error message shown • Invalid data not saved • Form indicates error field | Must Have | 7 min | SOC 2 Processing Integrity test
TEST2-SOC2-PI-002 |  | SOC 2 - Processing Integrity | Verify error handling in application | Negative | • Ability to trigger error condition | 1. Navigate to application 2. Trigger error condition 3. Observe error handling 4. Verify graceful recovery | • Error handled gracefully • User-friendly message shown • No data corruption • Error logged for review | Must Have | 10 min | SOC 2 Processing Integrity test
TEST2-SOC2-PI-003 |  | SOC 2 - Processing Integrity | Verify transaction audit trail | Happy Path | • Audit logging enabled | 1. Perform transaction in application 2. Navigate to audit log 3. Locate transaction entry 4. Verify logged details | • Transaction logged • All relevant fields captured • Timestamp accurate • User identity recorded | Must Have | 7 min | SOC 2 Processing Integrity test
TEST2-SOC2-PI-004 |  | SOC 2 - Processing Integrity | Verify calculation accuracy | Happy Path | • Known calculation scenario • Expected results calculated | 1. Enter known input values 2. Execute calculation 3. Compare result to expected 4. Verify accuracy | • Result matches expected value • Calculation documented • Rounding handled correctly | Must Have | 10 min | SOC 2 Processing Integrity test
TEST2-SOC2-PRI-011 |  | SOC 2 - Privacy | Verify privacy notice is displayed | Happy Path | • Privacy notice configured • New user scenario available | 1. Navigate to registration/signup 2. Locate privacy notice link 3. Review privacy notice content 4. Verify completeness | • Privacy notice accessible • Notice is current and complete • Easy to understand • Contact information provided | Should Have | 5 min | SOC 2 Privacy test
TEST2-SOC2-PRI-012 |  | SOC 2 - Privacy | Verify consent collection | Happy Path | • Consent mechanism configured | 1. Navigate to data collection point 2. Verify consent request displayed 3. Provide consent 4. Verify consent recorded | • Consent clearly requested • Options clearly explained • Consent recorded with timestamp • User can review consent status | Must Have | 5 min | SOC 2 Privacy test
TEST2-SOC2-PRI-013 |  | SOC 2 - Privacy | Verify opt-out functionality | Happy Path | • User with active consent • Opt-out mechanism available | 1. Log in as user with consent 2. Navigate to privacy settings 3. Exercise opt-out option 4. Verify opt-out processed | • Opt-out option available • Opt-out confirmation received • Consent status updated • Data processing stopped | Must Have | 7 min | SOC 2 Privacy test
TEST2-SOC2-PRI-014 |  | SOC 2 - Privacy | Verify data deletion request | Happy Path | • Data deletion mechanism available • User data exists | 1. Submit data deletion request 2. Verify request acknowledged 3. Check deletion status 4. Verify data removed | • Request mechanism available • Request acknowledged • Deletion completed within policy timeframe • Confirmation provided | Should Have | 15 min | SOC 2 Privacy test
TEST2-SOC2-PRI-015 |  | SOC 2 - Privacy | Verify data subject access request | Happy Path | • DSAR mechanism available | 1. Submit data access request 2. Verify identity as required 3. Receive data export 4. Verify data completeness | • Access request mechanism available • Identity verification required • Data provided in usable format • All personal data included | Should Have | 15 min | SOC 2 Privacy test

## User Stories
Story ID | Title | User Story | Priority | Role | Acceptance Criteria | Quality Flags | Source Row
TEST2-RECRUIT-001 | Number (N) Invited | As a research coordinator, I want to track number (N) of patients who received invitations, so that Core metric for outreach effectiveness | High | research coordinator | • ACCEPTANCE CRITERIA: • Count of invited patients displays accurately • Metrics are segmented by program/channel • Funnel shows progression from invitation to enrollment • Aggregated view available (not patient-level by default) • Data exportable for offline analysis • Historical trends visible for comparison • Conversion rates calculated correctly between stages • Data loads within 1 seconds • Visual displays Number (N) Invited with clear labels • Data is segmented/filterable by channel • Display updates when underlying data changes • User can only view data they have permission to access • Empty state shows helpful message when no data exists • • SUCCESS METRICS: • Zero discrepancy between source consent records and dashboard • All consent status changes reflected within 1 minutes • Data refresh completes within 15 minutes of source update • 100% data accuracy between source and display • Dashboard available 99.9% of uptime • Page load time under 3 seconds for 95th percentile | vague_language, needs_clarification | 2
TEST2-RECRUIT-002 | Program Recruitment Comparison | As a research coordinator, I want to identify recruitment volume by program, so that Reveals geographic or operational biases | Medium | research coordinator | • ACCEPTANCE CRITERIA: • Count of patients patients displays accurately • Metrics are segmented by program/channel • Funnel shows progression from invitation to enrollment • Aggregated view available (not patient-level by default) • Data exportable for offline analysis • Historical trends visible for comparison • Conversion rates calculated correctly between stages • Data loads within 3 seconds • Visual displays Program Recruitment Comparison with clear labels • Data is segmented/filterable by channel • Display updates when underlying data changes • User can only view data they have permission to access • Empty state shows helpful message when no data exists • • SUCCESS METRICS: • Zero discrepancy between source consent records and dashboard • All consent status changes reflected within 3 minutes • Data refresh completes within 15 minutes of source update • 100% data accuracy between source and display • Dashboard available 99.9% of uptime • Page load time under 3 seconds for 95th percentile | vague_language | 4
TEST2-RECRUIT-003 | Consent Flow Drop-off Tracking | As a research coordinator, I want to see where users stop in the consent process, so that Improves UX and conversion | Medium | research coordinator | • ACCEPTANCE CRITERIA: • Count of patients patients displays accurately • Metrics are segmented by program/channel • Funnel shows progression from invitation to enrollment • Aggregated view available (not patient-level by default) • Data exportable for offline analysis • Historical trends visible for comparison • Conversion rates calculated correctly between stages • Data loads within 3 seconds • Visual displays Consent Flow Drop-off Tracking with clear labels • Data is segmented/filterable by date range • Display updates when underlying data changes • User can only view data they have permission to access • Empty state shows helpful message when no data exists • • SUCCESS METRICS: • Zero discrepancy between source consent records and dashboard • All consent status changes reflected within 3 minutes • Data refresh completes within 15 minutes of source update • 100% data accuracy between source and display • Dashboard available 99.9% of uptime • Page load time under 3 seconds for 95th percentile | None | 5
TEST2-RECRUIT-004 | Email Engagement Tracking | As a research coordinator, I want to monitor if emails are opened or ignored, so that Optimizes communication strategy | High | research coordinator | • ACCEPTANCE CRITERIA: • Count of patients patients displays accurately • Metrics are segmented by program/channel • Funnel shows progression from invitation to enrollment • Aggregated view available (not patient-level by default) • Data exportable for offline analysis • Historical trends visible for comparison • Conversion rates calculated correctly between stages • Data loads within 3 seconds • Visual displays Email Engagement Tracking with clear labels • Data is segmented/filterable by date range • Display updates when underlying data changes • User can only view data they have permission to access • Empty state shows helpful message when no data exists • • SUCCESS METRICS: • Zero discrepancy between source consent records and dashboard • All consent status changes reflected within 3 minutes • Data refresh completes within 15 minutes of source update • 100% data accuracy between source and display • Dashboard available 99.9% of uptime • Page load time under 3 seconds for 95th percentile | None | 6
TEST2-RECRUIT-005 | Reminder Email Opt-Out Tracking | As a research coordinator, I want to monitor which users opt out of reminder emails, so that Ensures effective tracking should a participant want to change their mind in the future+C9I7C7 | High | research coordinator | • ACCEPTANCE CRITERIA: • Count of patients patients displays accurately • Metrics are segmented by program/channel • Funnel shows progression from invitation to enrollment • Aggregated view available (not patient-level by default) • Data exportable for offline analysis • Historical trends visible for comparison • Conversion rates calculated correctly between stages • Data loads within 3 seconds • Visual displays Reminder Email Opt-Out Tracking with clear labels • Data is segmented/filterable by date range • Display updates when underlying data changes • User can only view data they have permission to access • Empty state shows helpful message when no data exists • • SUCCESS METRICS: • Zero discrepancy between source consent records and dashboard • All consent status changes reflected within 3 minutes • Data refresh completes within 15 minutes of source update • 100% data accuracy between source and display • Dashboard available 99.9% of uptime • Page load time under 3 seconds for 95th percentile | needs_clarification | 7
TEST2-RECRUIT-006 | On-demand Patient Lists | As a research coordinator, I want to need to be able to pull list of patients who have declined to participate in the registry, consented, opted-in for future research, etc., so that Applicable for future studies that we want to identify cohorts for | High | research coordinator | • ACCEPTANCE CRITERIA: • Count of consented patients displays accurately • Metrics are segmented by program/channel • Funnel shows progression from invitation to enrollment • Aggregated view available (not patient-level by default) • Data exportable for offline analysis • Historical trends visible for comparison • Conversion rates calculated correctly between stages • Data loads within 1 seconds • Visual displays On-demand Patient Lists with clear labels • Data is segmented/filterable by date range • Display updates when underlying data changes • User can only view data they have permission to access • Empty state shows helpful message when no data exists • • SUCCESS METRICS: • Zero discrepancy between source consent records and dashboard • All consent status changes reflected within 1 minutes • Data refresh completes within 15 minutes of source update • 100% data accuracy between source and display • Dashboard available 99.9% of uptime • Page load time under 3 seconds for 95th percentile | vague_language, needs_clarification | 9
TEST2-RECRUIT-007 | Time on Consent Form | As a research coordinator, I want to track amount of time spent on each consent form page, so that Indicates how patients are interacting with the content of the consent form | Medium | research coordinator | • ACCEPTANCE CRITERIA: • Count of patients patients displays accurately • Metrics are segmented by program/channel • Funnel shows progression from invitation to enrollment • Aggregated view available (not patient-level by default) • Data exportable for offline analysis • Historical trends visible for comparison • Conversion rates calculated correctly between stages • Data loads within 3 seconds • Visual displays Time on Consent Form with clear labels • Data is segmented/filterable by date range • Display updates when underlying data changes • User can only view data they have permission to access • Empty state shows helpful message when no data exists • • SUCCESS METRICS: • Zero discrepancy between source consent records and dashboard • All consent status changes reflected within 3 minutes • Data refresh completes within 15 minutes of source update • 100% data accuracy between source and display • Dashboard available 99.9% of uptime • Page load time under 3 seconds for 95th percentile | None | 10
TEST2-RECRUIT-008 | Saliva Kit Ordering | As a research coordinator, I want to enables Discover Research team to order saliva kits via Propel dashboard for participants that opted-in for population sequencing protocol, so that Reduces manual workflows and increases effiency for large-scale population sequencing across broad and program-specific recruitment pathways | Medium | research coordinator | • ACCEPTANCE CRITERIA: • Count of patients patients displays accurately • Metrics are segmented by program/channel • Funnel shows progression from invitation to enrollment • Aggregated view available (not patient-level by default) • Data exportable for offline analysis • Historical trends visible for comparison • Conversion rates calculated correctly between stages • Data loads within 3 seconds • Visual displays Saliva Kit Ordering with clear labels • Data is segmented/filterable by date range • Display updates when underlying data changes • User can only view data they have permission to access • Empty state shows helpful message when no data exists • • SUCCESS METRICS: • Zero discrepancy between source consent records and dashboard • All consent status changes reflected within 3 minutes • Data refresh completes within 15 minutes of source update • 100% data accuracy between source and display • Dashboard available 99.9% of uptime • Page load time under 3 seconds for 95th percentile | None | 12
TEST2-RECRUIT-009 | MyChart Recruitment Cross Validation | As a research coordinator, I want to cross validate participants entering through the MyChart recruitment pathway against existing e-consent records in Propel to prevent duplicate enrollment from other recruitment pathways. Once cross validation is confirmed, a patient is allowed to proceed with consent if no consent exists or presented with a screen that notes that they have already been enrolled if validation notes a consent exists, so that Prevents redundant consent submission, and reduces confusion for participants recruited from other recruitment pathways | High | research coordinator | • ACCEPTANCE CRITERIA: • Count of enrolled patients displays accurately • Metrics are segmented by program/channel • Funnel shows progression from invitation to enrollment • Aggregated view available (not patient-level by default) • Data exportable for offline analysis • Historical trends visible for comparison • Conversion rates calculated correctly between stages • Data loads within 3 seconds • Visual displays MyChart Recruitment Cross Validation with clear labels • Data is segmented/filterable by date range • Display updates when underlying data changes • User can only view data they have permission to access • Empty state shows helpful message when no data exists • • SUCCESS METRICS: • Zero discrepancy between source consent records and dashboard • All consent status changes reflected within 3 minutes • Data refresh completes within 15 minutes of source update • 100% data accuracy between source and display • Dashboard available 99.9% of uptime • Page load time under 3 seconds for 95th percentile | None | 13
TEST2-RECRUIT-010 | Multi-Study Dashboard | As a research coordinator, I want to show a personalized list of available studies on the patient dashboard; each study appears as a collapsible accordion with shorthand details and a "Learn more/Sign Up" action, so that Centralizes options, reduces navigation friction, and increases conversion by surfacing all eligible studies in one place with quick-scan information | Medium | research coordinator | • ACCEPTANCE CRITERIA: • Count of enrolled patients displays accurately • Metrics are segmented by program/channel • Funnel shows progression from invitation to enrollment • Aggregated view available (not patient-level by default) • Data exportable for offline analysis • Historical trends visible for comparison • Conversion rates calculated correctly between stages • Data loads within 3 seconds • Visual displays Multi-Study Dashboard with clear labels • Data is segmented/filterable by date range • Display updates when underlying data changes • User can only view data they have permission to access • Empty state shows helpful message when no data exists • • SUCCESS METRICS: • Zero discrepancy between source consent records and dashboard • All consent status changes reflected within 3 minutes • Data refresh completes within 15 minutes of source update • 100% data accuracy between source and display • Dashboard available 99.9% of uptime • Page load time under 3 seconds for 95th percentile | None | 14
TEST2-RECRUIT-011 | SMS Outreach Reminders | As a research coordinator, I want to allows for researchers to reach out to patients via SMS through the platform, so that Increases multichannel outreach to potential participants | High | research coordinator | • ACCEPTANCE CRITERIA: • Count of patients patients displays accurately • Metrics are segmented by program/channel • Funnel shows progression from invitation to enrollment • Aggregated view available (not patient-level by default) • Data exportable for offline analysis • Historical trends visible for comparison • Conversion rates calculated correctly between stages • Data loads within 2 seconds • Visual displays SMS Outreach Reminders with clear labels • Data is segmented/filterable by channel • Display updates when underlying data changes • User can only view data they have permission to access • Empty state shows helpful message when no data exists • • SUCCESS METRICS: • Zero discrepancy between source consent records and dashboard • All consent status changes reflected within 2 minutes • Data refresh completes within 15 minutes of source update • 100% data accuracy between source and display • Dashboard available 99.9% of uptime • Page load time under 3 seconds for 95th percentile | needs_clarification | 16

## Traceability Matrix
Requirements Traceability Matrix
Coverage Summary
Total Requirements: | 11 | Total Test Cases: | 207
Full Coverage: | 9 (81.8%) | Partial Coverage: | 2 (18.2%) | No Coverage: | 0 (0.0%)
Compliance Test Coverage
Part11: | 36 tests | HIPAA: | 25 tests | SOC2: | 25 tests
Detailed Traceability
Req ID | Requirement | Story ID | Story Title | Test Cases | Compliance | Status
Reviewed Option C, okay to proceed once final confirmation is received on viability. For 3a, can you clarify if through assessment/appropriate channel means that the patient would be linked to where they left off after completing their clinical program assessment (I.e., they get to the accordion to see the intro about Discover and navigate away/close the window and then receive a reminder.) | Track number (N) of patients who received invitations | TEST2-RECRUIT-001 | Number (N) Invited | TEST2-RECRUIT-001, TEST2-RECRUIT-002, TEST2-RECRUIT-003 (+21 more) | HIPAA, Part11 | Full
REQ-ROW4 | Identify recruitment volume by program | TEST2-RECRUIT-002 | Program Recruitment Comparison | TEST2-RECRUIT-012, TEST2-RECRUIT-013, TEST2-RECRUIT-014 (+8 more) | None | Full
REQ-ROW5 | See where users stop in the consent process | TEST2-RECRUIT-003 | Consent Flow Drop-off Tracking | TEST2-RECRUIT-023, TEST2-RECRUIT-024, TEST2-RECRUIT-025 (+8 more) | None | Full
Agree to move forward with rejected email tracking with long-term intergration into the analytics dashboard. Advise that we integrate it as an actionable metric that project coordinators can click on to use an alternative pathway to contact the patient (e.g., email kicked back, project coordinator reviews kickbacks via analytics dashboard and can click to send SMS messages to those patients. | Monitor if emails are opened or ignored | TEST2-RECRUIT-004 | Email Engagement Tracking | TEST2-RECRUIT-034, TEST2-RECRUIT-035, TEST2-RECRUIT-036 (+8 more) | None | Full
Reviewed and okay to proceed with no additional notes. | Monitor which users opt out of reminder emails | TEST2-RECRUIT-005 | Reminder Email Opt-Out Tracking | TEST2-RECRUIT-045, TEST2-RECRUIT-046, TEST2-RECRUIT-047 (+19 more) | SOC2 | Full
Reviewed requirements and no further notes. Okay to move forward. | Need to be able to pull list of patients who have declined to participate in the registry, consen... | TEST2-RECRUIT-006 | On-demand Patient Lists | TEST2-RECRUIT-056, TEST2-RECRUIT-057, TEST2-RECRUIT-058 (+18 more) | HIPAA, Part11 | Full
REQ-ROW10 | Track amount of time spent on each consent form page | TEST2-RECRUIT-007 | Time on Consent Form | TEST2-RECRUIT-067, TEST2-RECRUIT-068, TEST2-RECRUIT-069 (+8 more) | None | Full
REQ-ROW12 | Enables Discover Research team to order saliva kits via Propel dashboard for participants that op... | TEST2-RECRUIT-008 | Saliva Kit Ordering | TEST2-RECRUIT-078, TEST2-RECRUIT-079, TEST2-RECRUIT-080 (+8 more) | None | Full
REQ-ROW13 | Cross validate participants entering through the MyChart recruitment pathway against existing e-c... | TEST2-RECRUIT-009 | MyChart Recruitment Cross Validation | TEST2-RECRUIT-089, TEST2-RECRUIT-090, TEST2-RECRUIT-091 (+8 more) | None | Partial
REQ-ROW14 | Show a personalized list of available studies on the patient dashboard; each study appears as a c... | TEST2-RECRUIT-010 | Multi-Study Dashboard | TEST2-RECRUIT-100, TEST2-RECRUIT-101, TEST2-RECRUIT-102 (+8 more) | None | Partial
Nick to reach out to Andrew for template. Draft language in process with Discover Team. | Allows for researchers to reach out to patients via SMS through the platform | TEST2-RECRUIT-011 | SMS Outreach Reminders | TEST2-RECRUIT-111, TEST2-RECRUIT-112, TEST2-RECRUIT-113 (+14 more) | HIPAA, Part11 | Full
Identified Gaps
REQ-ROW13 | May need HIPAA compliance tests
REQ-ROW14 | May need HIPAA compliance tests